ECP-2008-DILI-538025

JUDAICA Europeana

Final Progress Report

| Deliverable number | D1.8 |
| --- | --- |
| Dissemination level | Confidential |
| Delivery date | 31 January 2012 |
| Status | Final Version |
| Author(s) | Lena Stanley-Clamp, Dov Winer, Pier Giacomo Sola, Rachel Heuberger, Jean-Claude Kuperminc, David Klein |

eContentplus

This project is funded under the eContentplus programme, 
a multiannual Community programme to make digital content in Europe more accessible, usable and exploitable.

Table of Contents

1.	Summary	3

2.	Introduction	3

3.	The  Achievements of the Project	5

3.1	Digital content provided by Judaica Europeana	5

3.2	Solutions to the challenges of ingesting  diverse domain content	8

3.3	Digital humanities	9

3.4	Linked Open Data and Vocabularies: Pioneering surveys and work by Judaica Europeana	10

3.5	Dissemination activities	10

4.	Actions taken following the Intermediate Review	16

5.	Status	……………………………………………………………………………………….18

5.1	GANTT Table	18

5.2	Overview of Work Packages	20

6.	Deliverables Status	41

7.	Conclusions	43

Annex 1:	List of Academic Advisory Group Members	44

Annex 2:	Visitors’ statistics through Googleanalytics	45

Annex 3:	Highlights of Dissemination and Awareness activities	59

Annex 3.1	Conferences, workshops and other events	59

Annex 3.2 	 Judaica Europeana in the media	71

Annex 3.3:	 Stella di David e tricolore, a crowd sourcing content initiative	73

# 1.	Summary

This Final Report on Judaica Europeana focuses on the many achievements of the project. It highlights the fact that Judaica Euopeana exceeded its target in content provision by reaching  3,553,063 pages/objects. Judaica Europeana is currently ranked as the 14th largest provider to Europeana in terms of metadata records and the 4th largest provider of sound (soon to be placed 3rd following forthcoming ingestion of additional sets).   Other achievements presented include the work in the areas of knowledge management, controlled vocabularies and digital humanities. The extent and quality of the dissemination work is also presented.

The report outlines  the actions taken to address the issues raised by the Intermediate Review. It presents overviews of the work carried out by each Work Package during the last two years. More detailed information on the work accomplished by the work packages is to be found in the four  periodic reports. The Annexes provide supporting documentation, which has not been presented before.

# 2.	Introduction

JUDAICA EUROPEANA supports Europeana,  Europe’s libraries, archives and museums online, to reach a comprehensive coverage of the theme of Cities. Jews occupied a central role in the evolution of the modern city; their presence and stake in urban culture has been so high as to render them the symbolic equivalent of the city itself.  The project is anchored in a network of leading European institutions with substantial content holdings that document Jewish contribution to the development of European cities. Its objectives are:

- to encourage and support holders of Jewish content to identify elements of their collections that document the role, creativity and self-expression of Jews in European Cities so that this content may be processed and integrated into Europeana under the theme of Cities.

- to support the digitisation of such content (when required) and its aggregation into a virtual coherent thematic collection able to be fully integrated into Europeana.

- to coordinate standards across the participating institutions and holders of such thematic content in view of their harmonization to the metadata and interoperability requirements of Europeana.

- to identify, evaluate and support the implementation of a set of knowledge management tools. The deployment of such tools will enable the underlying community of practice to adapt and apply controlled vocabularies, thesauri and ontologies for the indexing, retrieval and re-use of the aggregated content in the area of interest.

JUDAICA has (1) provided a substantial amount of digitised resources for EUROPEANA (2) increased the re-use of such resources through an energetic dissemination (3) disseminated the use of standards assuring the compatibility of content to EUROPEANA requirements and demonstrated semantic interoperability  (4) involved the relevant community of knowledge and practice in a pilot that will demonstrate the added value of digital access in the thematic domain for scholarship and curatorial purposes.

JUDAICA has digitised a large quantity of  books, newspapers,  archive materials and press clippings as well as  photographs, postcards and a vast quantity of sound recordings. It also has involved additional Associate Partners who hold digitised resources in the thematic domain.

Judaica Europeana has contributed to all the above mentioned objectives, as specified in the following  pages.  The management and coordination tasks have been implemented effectively with due respect to the contractual tasks requested by the European Commission and in parallel with the dissemination and awareness actions. The work of Judaica Europeana has been carried out in the frame of its five work packages.

# 3.	The  Achievements of the Project

## 3.1	Digital content provided by Judaica Europeana

The main task of Europeana projects and Judaica Europeana among them is to bring substantial amounts of digitised content to  Europeana. We present below the table of the contents uploaded. The total quantity is well over the target indicated in the success indicators in the Description of Work. Judaica Europeana was expected to link 3,100,000 digitized cultural objects to Europeana. We are pleased to report that the total quantity achieved to-date is c. We present below the breakdown of the Judaica ingested content with types of objects, metadata and ranking by Europeana. Judaica Europeana is the 14th largest provider of content and currently 4th largest provider of Sound, soon to be ranked in 3rd place with the forthcoming addition of new sound content from the Centre francais des musiques juives.

| Europeana set | Data provider | Country | Ingestion plan set | TEXT metadata records | TEXT digitized objects | IMAGE metadata records | IMAGE digitized objects | SOUND metadata records | SOUND digitized objects | VIDEO metadata records | VIDEO digitized objects | Total metadata records | Total digitized objects |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09301 | Medem | France | 78 rpm |  |  |  |  | 690 | 690 |  |  | 690 | 690 |
| 09302 | Frankfurt | Germany | Freimann Collection | 6.317 | 975.989 |  |  |  |  |  |  | 6.317 | 975.989 |
| 09303 | Medem | France | 33 rpm |  |  |  |  | 3.536 | 3.187 |  |  | 3.536 | 3.187 |
| 09304 | Medem | France | Books | 874 | 209.869 |  |  |  |  |  |  | 874 | 209.869 |
| 09305 | AIU | France | Books | 260 | 46.237 | 226 | 226 |  |  |  |  | 486 | 46.463 |
| 09306 | CFMJ | France | Records |  |  |  |  | 14.045 | 14.613 |  |  | 14.045 | 14.613 |
| 09307 | JML | UK |  | 7.955 | 7.955 | 6.881 | 6.881 |  |  |  |  | 14.836 | 14.836 |
| 09308 | Frankfurt | Germany | Yiddish Prints | 750 | 123.277 |  |  |  |  |  |  | 750 | 123.277 |
| 09309 | Frankfurt | Germany | Hebrew Manuscripts | 344 | 73.961 |  |  |  |  |  |  | 344 | 73.961 |
| 09310 | Frankfurt | Germany | Frankfurt Collection | 568 | 39.773 |  |  |  |  |  |  | 568 | 39.773 |
| 09311 | AIU | France | Books+Periodicals | 320 | 35.382 | 28 | 28 |  |  |  |  | 348 | 35.410 |
| 09312 | Akadem | France |  |  |  |  |  |  |  | 1.849 | 1.849 | 1.849 | 1.849 |
| 09313 | JHM | Netherlands |  |  |  | 13.750 | 13.750 |  |  |  |  | 13.750 | 13.750 |
| 09314 | JMG | Greece | All |  |  | 26.206 | 26.206 |  |  |  |  | 26.206 | 26.206 |
| 09315 | MILEV | Hungary | Postcards |  |  | 2.002 | 2.002 |  |  |  |  | 2.002 | 2.002 |
| 09316 | JHI | Poland |  | 219.848 | 219.848 |  |  |  |  |  |  | 219.848 | 219.848 |
| 09317 | Toledo | Spain | Books | 257 | 78.800 |  |  |  |  |  |  | 257 | 78.800 |
| 09318 | Palatina | Italy |  | 170 | 58.128 |  |  |  |  |  |  | 170 | 58.128 |
| 09319 | Frankfurt | Germany | Compact Memory | 74.399 | 665.975 |  |  |  |  |  |  | 74.399 | 665.975 |
| 09320 | AIU | France | Books+Videos | 169 | 25.017 | 64 | 64 |  |  | 8 | 8 | 241 | 25.089 |
| 09321 | Medem | France | Books+Photographs | 714 | 168.786 | 185 | 185 |  |  |  |  | 899 | 168.971 |
| 09322 | Medem | France | Periodicals | 3.418 | 13.668 |  |  |  |  |  |  | 3.418 | 13.668 |
| 09323 | AIU | France | Photographs |  |  | 8.068 | 8.068 |  |  |  |  | 8.068 | 8.068 |
| 09324 | AIU | France | Books+Periodicals | 775 | 56.154 | 498 | 498 |  |  |  |  | 1.273 | 56.652 |
| 09325 | Medem | France | Cassettes+Photographs |  |  | 202 | 202 | 528 | 490 |  |  | 730 | 692 |
| 09326 | CFMJ | France | Records+Scores |  |  | 823 | 823 | 2.160 | 1.981 |  |  | 2.983 | 2.804 |
| 09327 | Akadem | France |  |  |  |  |  |  |  | 94 | 94 | 94 | 94 |
| 09328 | AIU | France | Archives | 7.320 | 619.236 |  |  |  |  |  |  | 7.320 | 619.236 |
| 09329 | MILEV | Hungary |  | 2.928 | 17.311 | 1.294 | 1.294 |  |  |  |  | 4.222 | 18.605 |
| 09330 | JML | UK | Audio files | 149 | 149 |  |  | 310 | 310 |  |  | 459 | 459 |
| 09331 | NLI | Israel | Rare Books+Manuscripts | 951 | 120.317 |  |  |  |  |  |  | 951 | 120.317 |
| 09332 | Venice | Italy | All | 38.597 | 38.597 |  |  |  |  |  |  | 38.597 | 38.597 |
| 09333 | Toledo | Spain | Artifacts |  |  | 2.381 | 2.381 |  |  |  |  | 2.381 | 2.381 |
| 09334 | Medem | France | Audio |  |  |  |  | 1.726 | 1.602 |  |  | 1.726 | 1.602 |
| 09335 | CFMJ | France | Audio |  |  |  |  | 652 | 646 |  |  | 652 | 646 |
| 09336 | Medem | France | Periodicals | 3.371 | 15.462 |  |  |  |  |  |  | 3.371 | 15.462 |
| TOTAL |  |  |  | 370.454 | 3.609.891 | 62.608 | 62.608 | 23.647 | 23.519 | 1.951 | 1.951 | 458.660 | 3.697.969 |
| Europeana provider rank | 8 |  | 17 |  | 3 |  | 7 |  | 15 |  |

## 3.2	Solutions to the challenges of ingesting  diverse domain content

The diversity of Judaica Europeana Partners’ collections posed great challenges in their mapping, ingestion and uploading to Europeana. The solutions developed by Judaica Europeana to resolve these problems constitute an important achievement which could benefit other projects and serve as guidelines for content providers. The process and the solutions are therefore described below at some length.

After extensive consultations and experimentation, two different platforms were used in the preparation of local metadata records for Europeana:

- Museum collections were processed in the Athena tool at early stages, then in a dedicated Judaica tool prepared by the NTUA team for the specific purposes of the Judaica Europeana project. Metadata records were mapped to LIDO, then transformed into ESE and published to Europeana;

- Library collections were aggregated using Repox, a standalone OAI-PMH server developed for the TELplus project. While part of the collections as the Frankfurt collection, were transformed directly into Europeana, for some collections, as  notably in the case of all French libraries, intermediary mappings in the Aleph ILS (Ex Libris) were inevitable for the proper rendition of these records in ESE;

- Several tools were considered and tested for the Archives section of the material, notably APEnet and NTUA’s Judaica tool. However, delays in EDM development have invariably forced us to flatten these collections and publish them through the two tools previously used for museum and library content.

The exclusive nature of links in the Europeana structure (i.e. only one possible link per metadata record) had to be addressed in a variety of methods depending on the source material:

- For audio records, as well as for AIU and Medem serials, originally containing numerous links to the entire collection in one metadata record, as many sub-records as links had to be created, each time with the appropriate volume or work description;

- Conversely, multiple files for pages of single volume monographs have been merged into a single pdf where possible, reducing considerably the number of records sent but rendering all pages infinitely more accessible to the Europeana end-user, through a single metadata record;

- Finally, where separating links between metadata records would distort the structure of the original document, but merging to a single file would limit facility of access to key points within a digital object (for instance multi-volume books or movements of the same musical work), we have opted for a link to a local interface, giving in turn access to these multiple links.

Rendering several fields mandatory in the latest version of ESE, at an advanced stage of the project, presented mainly problems with the LIDO2ESE translating schema.

- At the present stage, the europeana:rights and dc:language fields are still added manually by the NTUA team before sending the material to Europeana, provided rights and language information are constant throughout a given collection. Library collections, passing through Repox, are not concerned by this issue, with the exception of music notations – which are clearly TEXT files but not necessarily containing language material. The Europeana team is aware of the issue and has asked us to accept that these files be considered as IMAGE rather than TEXT for now.

In order to allow isShownAt links in Europeana throughout, public interfaces were created for collections previously lacking online record access (JHI, Venice, AIU photothèque). In two particular cases (AIU serials and archives), where an existing online catalogue architecture did not allow for a direct link on a metadata record level, a copy of the original database was made available on a participating online catalogue specifically for the Europeana user. For the serial collection this meant renouncing the copy protection found on the original interface. This, of course, could not be allowed for the archival material, which has thus been made available through the use of a free password upon request, in keeping with the guideline definition of Rights Reserved – Restricted Access.

30 second clips have been created for thousands of sound files to comply with copyright restrictions while still giving access to the distant end-user. In the case of the Jewish Museum London audio files, copies of all digital objects were created and placed on a server accessible for direct outside display to permit the creation of thumbnails by Europeana.

## 3.3	Digital humanities

Judaica Europeana has had  substantial achievements in promoting the use of digitised contents in the domain of interest for Digital Humanities purposes. An initial anchor for this effort was the collaboration established with two COST actions of the European Science Foundation: COST A32 – Open Scholarly Communities in the Web and COST IS0704 Interedition – An Interoperable Supranational Infrastructure for Digital Editions. Two important workshops were organized:

a) The Judaica Europeana  Digital Humanities workshop in collaboration with  COST A32 at the European Association for Jewish Studies Congress in Ravenna in July 2010.

b) Judaica Europeana and Interedition (COST IS0704) at the National Library in Jerusalem in October 2010.

These two workshops created at an early stage of the project a substantial group of scholars who became aware of the tools for Digital Humanities applications and the contents provided by Judaica Europeana. These events and scholars were supported by a resources page on Judaica website and by follow-up events at the University of Frankfurt, at King’s College London and the British Library.

The pilot for a knowledge management experiment involving a community of practice, carried out with the Haskala/Jewish Enlightenment project, thus became part of a wide effort to involve the scholarly  community. These efforts and achievements were recognized by the Center for Jewish History in New York with the invitation extended to Judaica Europeana to be one of just a few projects presented at the international conference “From Access to Integration.  Digital Technologies and the Study of Jewish History” in December 2011. Prof. Stefan Gradmann, a leading expert in the definition of requirements for Europeana, paid us a compliment by saying  that Judaica Europeana was among the Europeana projects that contributed most to Digital Humanities.

## 3.4	Linked Open Data and vocabularies: Pioneering surveys and work by Judaica Europeana

In May 2010, Europeana published the EDM – Europeana Data Model.. EDM was subsequently presented and discussed at the final meeting of WG3 of Europeana V1.0 which was held in Pisa in July 2010. Judaica Europeana followed closely the work of WG3 and participated in this workshop. The EDM is based on a Linked Data approach and its main standards anchors are OAI-ORE for metadata and SKOS for vocabularies.

Following this development, in August 2010, Judaica Europeana prepared an initial Internal Deliverable concerning the  implications of EDM; this paper was later included as a substantial part of D2.5 Semantic interoperability report with representation of selected controlled vocabularies in RDF/SKOS. This report surveyed the issues and concepts concerning a Linked Data approach and the crucial role that controlled vocabularies have to play in the new environment for enabling metadata enrichment, access to information and the development of new services. This Internal Deliverable also detailed a comprehensive program of work in this context related to the thematic domain. It suggested work to be carried out so that existing vocabularies in the Jewish domain be enabled to serve as an infrastructure for dealing with questions such as What? (concepts, objects) Who? (names) Where? (places) When? (time).

This Internal Deliverable was used in promoting the proposed work program among the partners and the leading institutions that developed and maintain controlled vocabularies and have the expertise to implement the proposed program. Much effort was invested in promoting this program among the leading Information Sciences experts and institutions such as the Association of Jewish Libraries, the National Library of Israel, Yad Vashem the Holocaust Memorial Authority, the Israel Museum Jerusalem and others. The first result of this effort is the development of a query service for Europeana based on the SKOSified vocabularies of the Israel Museum Jerusalem that is detailed below. It enables querying Europeana by browsing these vocabularies’ concepts tree; it also enables translation of searches using the multilingual features of these vocabularies.

## 3.5	Dissemination activities

The awareness raising and dissemination activities carried out by Judaica partners merit to be highlighted as a major achievement. A Google search for “judaica europeana” provides  “170,000 results in 0.32 seconds” (29.1.2012).

Judaica Europeana dissemination plan focused on the quality of the dissemination tools and on outreach to target audiences. The feedback on the newsletters, the multimedia presentations  and the website has been excellent. (‘I found your newsletter wonderfully informative and interesting.’ Judith C. Siegel,  Director of Academic and Public Programs, Center for Jewish History, New York; ‘This is extremely interesting. If there is a regular mailing list for the newsletter, we would much appreciate being on it.’ Suzanne Garment, Jewish Ideas Daily.) Judaica newsletters can be accessed at http://www.judaica-europeana.eu/Newsletter.html

3.5.1		Extensive programme of workshops, conferences and other events

Judaica organized or was presented at 100 successful events in 16 countries and 45 cities.  See Annex 3.1 with a list of Judaica Europeana events and numbers of participants.

Feedback from the participants in the Judaica Europeana Workshop at the British Library 30.10.11

3.5.2		Judaica Europeana in the media

The project has attracted extensive media coverage with articles on the  internet and press, blogs, and scholarly journals.  A partial list of recorded media coverage is presented in Annex 3.2.

3.5.3		Virtual exhibitions

Virtual exhibitions are great showcases for the digital collections of Judaica partners. They place images and documents in their historical and social contexts, and bring Jewish history and culture to life. The exhibitions are valuable tools for teachers, students, researchers, curators and others with an interest in European history and other subjects.  They enhance partners’ digital content and stimulate users to explore it further on Europeana, on the partners websites or visit the collections in person.

Judaica Europeana provided guidance and support to the partners in the production of virtual exhibitions. Partners developed new skills and expertise in this domain which was entirely new to them. The cooperation established with the Europeana staff led to the hosting and dissemination by Europeana of two online Judaica exhibitions of the highest quality. The exhibitions are accessible on the Judaica and partners’ websites.

Yiddish Theatre in London

This virtual exhibition from the Jewish Museum London reveals a fascinating history. From the late 19th century, Jewish immigrants from Eastern Europe brought a rich and expressive form of theatre to the East End of London. Plays were performed in Yiddish, the language spoken by Central and Eastern European Jews. They ranged from comedy to tragedy, drawing on Yiddish folk tales, adaptations of Shakespeare and stories of immigrant life. The early 20th century was the heyday of Yiddish theatre in London, with packed theatres and long queues for tickets.The exhibition contains an overview of the origins of Yiddish theatre, the Jewish  migrations from Eastern Europe and life in the East End of London. The narrative throws a spotlight on the people, buildings and plays that made Yiddish theatre in London so special. The visitors are taken on a guided tour of the unique collection of photographs, documents and objects held at the Jewish Museum London. http://exhibitions.europeana.eu/exhibits/show/yiddish-theatre-en

From Dada to Surrealism: Jewish Avant-Garde Artists from Romania 1910-1938

This online exhibition was curated by the Jewish Historical Museum, Amsterdam and produced in cooperation with Europeana.  It complemented the onsite exhibition held at the JHM in Amsterdam in 2011. In the early decades of the twentieth century, the art world was taken by storm by the experimentalism of Jewish artists: Tristan Tzara, Victor Brauner , Marcel Janco, and M. H. Maxy. They and other  Romanian artists were present at the birth of an influential avant-garde movement. The younger artists Jules Perahim and Paul Păun, inspired by their predecessors, were at the forefront of Surrealism. Their artistic practice extended to abstract and expressionist works and personal variations on Constructivism. This art movement, which challenged the established conventions, was at its origins also a revolt against the horrors of the First World War. The exhibition demonstrates the importance of the Jewish artists from Romania in the development of European avant-garde art. The artworks, photographs and video on show shed light on the relationship between Jewish identity and radical modernity. http://exhibitions.europeana.eu/exhibits/show/dada-to-surrealism-en

Jewish Britain: A History in 50 Objects

The exhibition showcases the collections of the Jewish Museum London.  Each object in the exhibition tells a story about the history of the Jewish community in Britain from medieval to modern times in towns and cities across the country. The collections hold around 28,000 objects, including Judaica (ceremonial art) and a social history collection covering subjects such as the East End of London  and the Holocaust. Jewish people have migrated to Britain for a variety of reasons and from a multitude of places:  from the first Jewish settlers from France in 1066, the immigrants from East-Central Europe in the 19th - 20th centuries and refugees from Nazism, to more recent newcomers such as Israelis and South Africans. The collections present stories of their origins, journeys and settlement.  The virtual exhibition themes include: migrations and settlement, working lives and trades, family life and home, growing up, military service, religious life and politics, charities and welfare, sports and leisure. http://www.jewishmuseum.org.uk/jewish-britain-about

A Virtual Tour of Jewish Frankfurt

This online exhibition was produced by Frankfurt University Library in cooperation with the Jewish Museum in Frankfurt, associate partner of Judaica Europeana.  It will be publicized and isseminated jointly with the Tourist Office of the City of Frankfurt.

Frankfurt has been a home to an important Jewish community which contributed greatly to the city’s development. Their history is embedded in the city’s architectural heritage. Conceived as a virtual tour, the exhibition takes the visitor to 16 sites of Jewish life in Frankfurt today. All these sites can be visited and are mostly still active. The tour shows the Jewish community centre, the Jewish day-school, the synagogue, the Jewish Museum, the cemetery, public places, historic buildings and monuments. The photographs have been taken recently, the texts give introductions about the sites’ history and connect to the addresses of the institutions that are featured and more information. The addresses are connected to Google map for easy location

http://en.juedisches-frankfurt.de/introduction

Judaica Europeana –Jewish cultural heritage on the web

This online exhibition presents some of the masterpieces of the digitized collection of the Frankfurt University Library as they were shown in an onsite exhibition in the Kunstbibliothek (Art-Library) of the Frankfurt University. The poster exhibition was curated by the Frankfurt University Library in cooperation with the Kunstbibliothek – Städelbibliothek of Frankfurt.

The topic of the exhibition was the project itself, Judaica Europeana, presenting posters of the structure of the network and its members as well as typical examples of the collection. The onsite exhibition was supplemented with the original books and drawings, thus highlighting the differences and benefits of the Judaica Europeana project. The images which can be explored online, demonstrate the variety of Jewish urban culture and contain posters of maps and photos of the Jewish quarter and typical Frankfurt scenery as well as drawings of prominent personalities, medieval manuscripts and music sheets.  A commentary on each of the exhibits provides the historical context of the development of Jewish life and culture. http://www.ub.uni-frankfurt.de/ssg/praesentation_europeana_ausstellung.pdf

Images of Greek Jews

This virtual exhibit from the Jewish Museum of Greece in Athens presents a selection of 20th century photographs from the Museum’s extensive photographic archive digitized in the framework of the Judaica Europeana project. Family portraits, school children, scouts and others groups from Athens, Chania, Corfu, Ioannina, Thessaloniki and Volos, before and after World War I and II, capture Greek Jews at formal or family occasions, school trips or simply at leisure. They convey a sense of a flourishing and well integrated community in a bygone era. The exhibition demonstrates the importance of the museum’s archive in the documentation of the history and culture of the Greek Jews.  Some of the photographs stand out, because they satisfy certain aesthetic criteria which place them on a higher plane, that of artistic photography.

http://www.jewishmuseum.gr/en/index.html

Jewish Neighbourhoods of Greece

This photographic exhibition from the Jewish Museum of Greece depicts, mostly, pre-war Jewish life in 12 communities around Greece: Athens, Saloniki, Volos, Larissa, Ioannina, Trikala, Verola, Chalikida, Corfu, Rhodes, Xanthi and Zakynthos.  The photographs show various aspects of Jewish life: how the Greek Jews lived as children or young adults, before the war and after its end. The photographs show their homes, occupations, entertainment and gatherings, holidays, family and friends, neighbours, recollections and changes brought on by the war. Thus, the visitor explores a vivid, though of necessity partial, image of a way of life rich in traditions and human relations, of a world that the war destroyed forever. The exhibition material includes photographs of the twelve communities, on which neighbourhood photos were collected. (Design based on Cooliris software.)

http://www.jewishmuseum.gr/en/index.html

Jewish postcards: Networking in Europe

This virtual exhibition from the Hungarian Jewish Archives in Budapest is based on their Vilmos Kohn collection, which has been digitized by Judaica Europeana. The collection contains over 1,000 postcards, mostly from East-Central Europe. The postcards became popular at the time when Jewish migration was a significant phenomenon. They were the best way of keeping alive the connections between family members dispersed in different countries and continents.

At the peak of the postcards’ popularity (1880-1918), they answered the need for self-representation of very diverse Jewish populations: the secular and traditional Jews, the Orthodox and Reform, the Zionists and others. Today, these picture postcards are important visual resources for research on Jewish identities and mentalities of the 19th and early 20th century. The themes of this exhibition include: greetings from the past, greetings from the old homelands and the New World, greetings from Zion, greetings from the battlefields of Europe, love greetings, representations of Biblical stories. The most popular postcards depict Jewish festivals and greetings. http://milev2.2kal.hu/exhibits/show/networking-in-europe

Alliance Israelite Universelle:  150 Years of Achievement in Education (1860-2010)

This exhibition celebrates 150 years since the establishment of the Alliance Israélite Universelle, an educational institution which created a vast network of schools in Morocco, Tunisia, Turkey, Ottoman Palestine, Egypt, Iraq, Syria and other countries. Hundreds of thousands of children have benefited from a broad-minded education provided in the French language and informed by the Jewish tradition. The Alliance helped enrich culturally the lives of generations of men and women while providing them with social and economic opportunities in wider society. Today, the Alliance does its work mainly in France, the United States, Morocco and Israel. It takes an active role in promoting Jewish culture across the world. The online exhibition accompanied the physical exhibition held at the City Hall in Paris in 2010. The online exhibition can be accessed at the partner’s website and on Judaica home page.

http://www.aiu.org/bibli/Expo-virtuel/Accueil-expo.html

The Star of David and the Tricolore: a crowd-sourced, user-generated initiative

Stella di David e Tricolore is a successful crowd-sourced, user-generated content initiative developed by MiBAC/ICCU in the framework of WP4. A Judaica Europeana space on the Culturaitalia portal invites users to provide archival material, publications, stories, videos and photographs relating to the history of the Jews in Italy in the 150 years since Italian unification. The Star of David features in effect a series of virtual exhibitions. A pro-active approach and dissemination events were held to publicize this inititative. More information and images are provided in Annex 3.3.

3.5.4		Sustainability of Judaica Europeana and extension of the network

Judaica Europeana succeeded in developing a model for the continuation of the project after the conclusion of the 2-year funded programme.  A Memorandum of Understanding (MOU) agreed by the partners will provide a framework for continued coollaboration with an extended network of partners. The agreed aims of the Judaica Europeana Consortium, which will operate in the new framework, are described in the MOU as follows:

The aims and purpose of the Judaica Europeana Consortium are to provide integrated online access to Jewish-content collections for the widest possible public. Judaica Europeana will serve as a conduit for the opportunities created by Europeana, the Semantic Web and the Open Linked Data environment for the partner institutions and their collections.

The purpose of the Judaica Europeana Consortium (from now on referred to as ‘JE’) is to provide continuity for the work carried out by the Judaica Europeana project which has been co-funded by the European Commission in the framework of Europeana.eu, the most important platform for Europe’s cultural heritage.

To pursue the above aims JE will continue to serve as the aggregator of Jewish content for Europeana, Europe’s Libraries, Museums and Archives online. The main objectives of JE are to  (a) identify relevant digital content in Europe and beyond which documents Jewish life in Europe; (b) support the content holders in preparing and adapting their metadata to the requirements of Europeana and (c) assist them in the ingestion and uploading process to Europeana.Furthermore, JE will seek to promote the dissemination and application of the relevant digitized content in various areas of cultural activity: scholarship and research; university teaching; education and community activities; virtual exhibitions and museum curatorship; professional development of cultural sector professionals; re-use of the contents for renewed cultural creation; and other related fields.

The leading partners UBFFM (project co-ordinator) and EAJC (project manager) have committed resources to the continuation of Judaica Europeana. For further detals and plans see D4.9 Final Exploitation Plan.The Judaica partners that have uploaded their collections will be supported in the enrichment of  their metadata and will work together on the dissemination of their digital collections. The extensive network of new content holders that wish to provide access to their digital collections or content that is being digitized includes:

Ben Uri Gallery – The London Jewish Museum of Art
Bibliotheca Rosenthaliana, Amsterdam
Center for Jewish History, New York
Central Zionist Archives, Jerusalem
Centre français des musiques juives, Paris

Columbia University Library
Jewish Historical Museum, Amsterdam
Jewish Museum Berlin 
Jewish Museum, Frankfurt/Main

Harvard University Library
Leopold Zunz Zentrum, Halle-Wittenberg
Ministerio de Cultura, Madrid
National Library of Israel, Jerusalem
Paris Yiddish Centre – Medem Library
Salomon Ludwig Steinheim Institut, Duisburg
Sephardi Museum, Toledo

# 4.	Actions taken following the Intermediate Review

The Intermediate Review of the project in January 2011 made the following  recommendations: (1) implementation of a suitable risk management policy (2) clarification of IPR issues (3) ongoing provision of information not covered by deliverables (4) concise evaluation policy (5) provision of recommendations to partners on the following matters so they are able to provide content to Europeana: multilingual access, IPR issues and business models.The following actions were taken to address the above issues:

Risk Management Policy

Immediately following the Intermediate Review, the partner Amitie, working in consultation with WP1 and the other WPs, prepared a Risk Register which identified and assessed the areas of risk and the steps that should be taken to remedy the problems that may arise.  An in-depth Risk Management Policy report was developed by Amitie subsequently and approved pending clarification on some technical matters.  A detailed internal deliverable Project Risk Analysis and Mitigation (PRAM) was distributed to the partners in June 2011. This document adopted a methodology that included (1) Identifying risks (2) Evaluating and prioritizing risks (3) Recording the findings (4) Deciding on preventive action/mitigation (5) Communicating the findings to the consortium.

The risk identification was a team effort involving those most familiar with the circumstances of the project. They issues and concerns raised at the intermediate review as well as a detailed analysis of the project work structure and deliverables list were examined. After their identification they were classified by their likelihood and consequences ({H} Catastrophic {M} Critical {Marginal}/ High {>70%}, Medium {30%<x<70%}, Low {<30%}. The identified risks were logged into the risk register using a form that provided a consistent basis for understanding the project risks and mitigation strategies; it served also as a tool for communication among the consortium members.

Preventive actions or mitigations have the purpose to lessen or reduce, if not eliminate, the adverse impact of known or perceived risks; they were jointly decided and added to the risk inventory as “mitigation strategy”.

IPR issues

Judaica Europeana joined and participated in the activities and meeting of the Council of Content Providers and Aggregators in which much of the efforts of Europeana concerning IPR were expended. There was a consistent effort by Europeana to draft a framework as open as possible and at the same time to try and address concerns raised by some constituencies. The result of this effort was the drafting of the Europeana Data Exchange Agreement and the Europeana Metadata Usage Guidelines.

The participation of the Judaica Europeana management in this process enabled it to inform the partners concurrently with the developments in this area.

Provision of information not covered by deliverables

The project used all the available tools for communications and dialogue between the partners, the associated partners, the Europeana staff and liaison person and the project officers. These included the project emailing lists, the website, the back office and the hundreds of bilateral and group email exchanges and phone calls.  Greater attention was paid to the description of work processes in presentations at partners’ meetings and in the periodic deliverables reports.

Concise evaluation policy

WP5 reviewed its work in the light of the recommendations made by the Review.  The evaluation of performance was extended to include the work of all Work Packages.  Self-assessment surveys were implemented online. WP 5 provided internal evaluation deliverables as well as close monitoring of the project output in real time. It prepared and distributed evaluation questionnaires at all consortium meetings and many events. It provided feedback to the partners and management on performance evaluation at the consortium meetings as well as in the successive drafts of the final evaluation report.

Multilingual access, IPR issues and business models

The intensive work carried out by the project in the area of controlled vocabularies enabled it to provide a pioneering service for multilingual access to Europeana. This service makes use of the SKOSified vocabularies of the Israel Museum Jerusalem presently available in Hebrew and English and soon to be available also in Arabic, Russian and French. This pilot was implemented by NTUA with input from the Europeana technical staff. In the first stage of the service users can query Europeana with Hebrew keywords that are translated using the vocabulary features.  The query, in English, is sent to Europeana which provides its own multilingual support. An additional service enabling multi-lingual browsing of Europeana using a thesaurus tree was installed on the Judaica website search page.

Partners received very detailed instructions how they can SKOSify their controlled vocabularies, map them to outstanding authorities, publish them as Linked Data and thus enable the enrichment of their metadata in Europeana.

IPR issues were discussed among partners (see more under IPR above).

The detailed Exploitation Plan deliverable developed by Judaica Europeana deals with the issues of sustainability and possible development of business models.

# 5.	Status

## 5.1	GANTT Table

The following table presents the overall plan of activities of the project, derived from the latest version of the Description of Work:

:

## 5.2	Overview of Work Packages

Work Package 1 – Project Management

Work package Description

| Work package number : | 1 | Start date: | 0 | End date: | 24 |
| --- | --- | --- | --- | --- | --- |
| Work package title: | Project Management |

Objectives for the period

To effectively manage the project to deliver the solutions developed in the Work Packages on time, to maintain cost and quality in accordance with the requirements of the grant agreement between the Commission and the project consortium. This will be done by providing: internal management and financial/administrative control of the project; planning of external strategic co-operation activities; building of both informal and formal relationships with other relevant projects and initiatives.

Description of work carried out and achievements

This WP is led by the European Association for Jewish Culture This work package provided the administrative and organisational capacity for the project start-up, implementation and development. It managed the coordination with the European Commission and ensured the communication and the circulation of information among the partners. it organized partners’ meetings and led the preparations for the Intermediate and Final Review. WP1 monitored and supported the work of the other work packages. Among the activities carried out during the reporting period, the following should be noted: Development and revision of work: WP1 ensured that all Work Packages reviewed their working plans at Consortium meetings in the light of issues arising, and corrective actions were agreed. Amendment to the contract and DoW. Following the identification of required corrective measures WP1 prepared and applied to the Commission for an amendment of the contract enabling the inclusion of a new partner, NTUA as well as other corrections. The inclusion of NTUA from February 2011 was necessary to provide the project with the technical capabilities it required that were not available until then. Co-option of Associate Partners: WP1 identified and approached many potential associate partners with the aim of aggregating their collections in Judaica Europeana. Progress depended on the extent to which the collections of the prospective partners were digitized or were ready for ingestion. Cooperation was agreed with 19 associated partners. Six of those associate partners were able to ingest their digital content by the end of the first 2 years of the project. Others such as Bibliotecca Rosenthaliana, Amsterdam, the Center for Jewish History, New York and Harvard University Library will be ready to do so in early 2012. The remaining current associate partners are in the process of digitizing collections and adapting their databases and metadata. Organisation of steering committee and plenary meetings with WP Leaders and partners. The following meetings were organised (minutes and presentations are available in the reserved area): 2010-01-25/26 London, UK Kick-off meeting 2010-05-10/11 London, UK 2nd Steering Committee and WP meetings 2010-07-27 Ravenna, 3rd Steering Committee and WP meetings 2010-11-15 Jerusalem, 4th Steering Committee and WP meetings 2011-02-6/7 Paris, Judaica Europeana 5th Steering Committee and WP meetings 2011-06-29/30 Budapest, Judaica Europeana 6th Steering Committee and WP meetings 2011-09-18/20 Warsaw, Judaica Europeana 6th Steering Committee and WP meetings Meetings of WP Leaders were organised in order to coordinate activities. These meetings were held through online conferencing facilities. Organisation and follow-up to the Internediate Review meeting with the European Commission. WP1 prepared the meeting by sending all relevant deliverables to the Commission on time and reviewing the presentations of the WP coordinators. WP1 acted and followed-up with other Work Packages and partners on addressing the recommendations of the Review. Mailing list: the Judaica@amitie.it mailing list was set up following the launch of the project. It served for the announcements and exchanges with all the partners With the increase of the number of associated partners an additional mailing list, judaicaassociates@amitie.it was established. Activation and maintenance of a back office area within the project’s website served toshare all documents, deliverables and presentations among the partners. Username and password to access the reserved area are available to the European Commission. See: http://project.judaica-europeana.eu Formation of the Academic Advisory Group (AAG) and its involvement in the project. WP1 in consultation with WP2 secured the cooperation of 15 academic experts at leading universities. The first meeting of the AAG took place during the Ravenna Congress of the European Association for Jewish Studies on July 29, 2010. Prof. Antony Polonsky is the Chair of the Group which inludes leading scholars involved in research and teaching of Jewish history and culture. They provided general guidance, helped disseminate Judaica to universities for teaching and research purposes, and provided evaluation of the academic and dissemination aspects of the project. The list of AAG members is attached to this report in Annex 1. The Management Team remained in regular contact with the Chairman and members of the Academic Advisory Group, consulting and exchanging ideas, informing about progress, involving them in workshops and conferences, and in evaluation. Contacts with the Europeana management: WP1 coordinator has been in regular contact with the Europeana Team: Julia Brungs, Martina Schoberova, Anne Marie Gerwaen, Jon Purday, David Haskiya. Judaica’s WP1 and WP3 have met and been in contact with Europeana’s technical team regarding metadata uploading. Judaica Europeana Management Team participated in Europeana conferences and Working Group meetings. WP1 Coodinator is a member of the Europeana Council of Aggregators. Both WP1 and WP3 have been in frequent contact with Europeana’s Ingestion Team regarding the uploading of metadata: Annelies van Nispen, Dimitra Atsidis‎. Cooperation with other projects from the Europeana cluster: (1) There have been regular contacts with the Athena project regarding the use of the Athena ingestion tool. Judaica Europeana representatives have participated in relevant Athena events; the training materials developed by Athena have been used by Judaica Europeana partners (2) The materials produced by the IMPACT project (British Library, partner in Judaica) were used by Judaica partners for reference. (3) Judaica Europeana representatives participated in WP3 of the Europeana V1.0 project and in its final meeting which defined the new Europeana Data Model. (4) Contacts were made with the EOD network (eBooks on Demand) http://www.books2ebooks.eu/partner.php5; with the APEnet and EuropeanaLocal projects including a presentation at EuropeanaLocal national conference in Madrid in 2010. (5) Judaica Europeana representatives participated in the meetings of Europeana Comms Group. (6)the EuropeanaTech conference in Vienna (4-5 October 2011) that concluded the Europeana Connect project and started the work on Europeana V2. (7) The contacts with the APEnet project regarding the APEnet tools developed for the ingestion of contents from archives were successful although we did not use this tool as it became available too late to begin experimenting with it. (8) Judaica Europeana representatives participated in the meeting of the Council of Europeana Content Providers and Aggregators. Review of Risk Management: WP1 and WP5 compiled and reviewed together the risk management register and which included the issues relating to the ingestion process and their solutions. Judaica Europeana sustainability. WP1 drafted and presented to the partners a model for the continuing development and maintenance of Judaica Europeana activities beyond the date of conclusion of the present contract. The model is based on the establishment of a MOU (Memorandum of Understanding) among the partners that enables the continuing governance of the activities. The model was accepted. The EAJC will serve as the Secretariat of the consortium and Dr. Rachel Heuberger of Frankfurt University will serve as its chair, while Pier Giacomo Sola of Amitie will serve as Deputy Chair. Based on this model, WP1 has already pursued and continues to seek opportunities for funding the follow-up of Judaica Europeana. As documented in the D4.9 Final Exploitation Plan, the EAJC Board has committed staff resources to JUdaica Europeana and UBFFM has created a part-time (50%) position in the Frankfurt University Library to ensure the continuation of the Judaica work. The deliverables D1.1, D1.2, D1.3, D1.4, D1.5, D1.6 and D1.7 have been prepared and delivered to the Commission on time. .

Deviation from work plan & remedial action

None.

Work Package 2 – Content selection, metadata alignment, knowledge management

Work package Description

| Work package number : | 2 | Start date: | 0 | End date: | 24 |
| --- | --- | --- | --- | --- | --- |
| Work package title: | Content selection, metadata alignment, knowledge management |

Objectives for the period

To provide EUROPEANA with a critical mass of content: To identify and select in the collections of the partners and Associated Partners a critical mass of cultural heritage resources that belong to the thematic domain, “Jews in European Cities” to be digitised. To identify already digitised resources that belong to the same domain. To align the metadata for this content to the EUROPEANA metadata requirements. To survey the existing metadata schema that are now being applied by the partners for the description of their digitised resources; Define and implement the necessary steps to align these schemas to the Metadata requirements defined for EUROPEANA To implement the required alignment through the work of experienced indexers. To survey and identify existing controlled vocabularies in the thematic domain area and establish and disseminate them throughout the domain: To adapt and implement controlled vocabularies (taxonomies, thesauri and ontologies) for advanced indexing and retrieval of the content, and to adapt them to the semantic interoperability requirements defined for EUROPEANA. To test the adequacy of the metadata and semantic interoperability in a pilot knowledge management system that will support the work of a community of practice of scholars and cultural heritage professionals in the thematic domain area.

Description of work carried out and achievements

This WP was coordinated by partner UB-FFM. WP2, in cooperation with all partners and content providers, produced 7 deliverables that fulfil its tasks: D 2.1 Audit on Judaica Europeana content including metadata, 1st version For this deliverable, a detailed questionnaire (available at the Judaica Europeana back office, in the WP2 section) was developed to support a detailed audit, assessment and selection of content to be digitised at the partner institutions’ collections, including analysis of quality and types of resources/assets, copyright and IPR issues, quantified targets for digitisation.as well as a detailed audit of available digitised resources. The questionnaire contained a survey of the existing metadata schema that are currently being applied by the partners for the description of their digitised resources. The accurate appraisal of content and metadata in use provided by the partners was delivered.The survey made apparent the multiplicity of standards and the wide range of metadata. as the Judaica Europeana partners different types of cultural heritage institutions including libraries, archives and museums. D2.2 First Report on Content Metadata Alignment with Europeana Requirements This deliverable presents the resulta of the Judaica Europeana survey in regard to content metadata alignment with Europeana requirements.WP2 activities were characterised by intensive exchanges and evaluation of the different metadata schema and how best to deal with the challenges involved in mapping such varied schemata to ESE (Europeana Semantic Elements). D 2.3 Audit report on Judaica content including metadata This deliverable shows the result of content identification and selection of ressources that belong to the thematic domain “Jews in European cities” and have been identified by the Judaica Europeana partners in their respective collections. In the course of digitization work processes have been successfully established at all partner institutions with regard to content selection and precedures for metadata alignment put in place according to the requirements of Europeana. Knowledge management experiment. WP2 delivered D2.7 Report on the deployment of a knowledge management system with a pilot focus group. WP2 defined the tasks for this pilot project and contracted Yaron Koren from Wikiworks.com to carry out the work of creating a knowledge management semantic environment for the scholars who developed the Haskala (Jewish Enlightenment) Database (University of Potsdam, Tel Aviv University and Bar Ilan University). In continuation, the work carried out by this WP was reported in the following deliverables: D2.4 Survey of Controlled Vocabularies relevant to the thematic domain This deliverable monitors developments concerning controlled vocabularies related to Jewish content and has involved in the project the principal existing initiatives related to indexing and digitisation of Jewish content. It was based on a detailed internal deliverable prepared by WP 2 concerning vocabularies. This internal deliverable – Jewish semantics in the Linked Data Semantic Web – Vocabularies – is available at http://www.judaica-europeana.eu/docs/jewish_vocabularies_LOD.pdf The contacts established with key institutions and experts included: the Research Libraries, Archives, and Special Collections Division (RAS) of the Association of Jewish Libraries; University of California, Berkeley, Magnes Collection; the Jewish Museum Berlin; the National Library of Israel; the Israel Museum Jerusalem (IMJ); Yad Vashem Holocaust Authority and individual experts. WP2 identified two pilot experiments concerning vocabularies: (1) Applying the thesaurus of the IMJ for multilingual access to Europeana (2) Possible implementation of the places controlled vocabulary of Yad Vashem for enriching Judaica Europeana metadata. D2.5 Semantic interoperability report with representation of selected controlled vocabularies in RDF/SKOS An initial version of this document was prepared in September 2010, as an Internal Deliverable of Judaica Europeana. This document engaged the interest of many stakeholders and enabled them to grasp better the vision that drives Europeana and seeks to establish a seamless universe of Cultural Heritage content embedded in the wider Linked Data web. The D2.5 deliverable outlines a program of actions concerning Jewish vocabularies. Its purpose is to enable the integration of content digitised by Judaica Europeana and many other related initiatives in the Web of structured data (Linked Data). This will enable access to Jewish knowledge greatly enriched by the professional communities that stored Jewish related expertise in databases and vocabularies. D2.6 Second report on content metadata alignment with EUROPEANA requirements The first part of this report summarizes content identification and metadata alignment. The partners have detailed the resources already digitized as well as the material still to be digitized and selected for ingestion into Europeana in the course of the project. The second part presents the survey regarding metadata alignment and gives detailed information about the metadata schema used in the partners’ institutions and their adaptation to Europeana requirements. The third part of this report lists the existing metadata standards that are in use by the partner institutions and reflects the multiplicity of standards and wide range of metadata alignment practiced by archives, libraries and museums with Judaica content. At the end of the report, outstanding examples from the different institutions are presented that have been already ingested. D2.7 Report on the deployment of the knowledge management system with a pilot focus group This deliverable provides a survey of the issues involved in the application of the new EDM, Europeana Data Model, in supporting scholarship within a Digital Humanities approach. Some conceptual frameworks are presented including details concerning annotation and providing support for communities of practice. The actual pilot experiment carried out by Judaica Europeana that focussed on the research project on the Jewish Enlightenment ‘Haskala: Building a modern Jewish Republic of Letters in the 18th and 19th Century’ is described. The report details the process through which Judaica Europeana sought to find the semantic tools appropriate for supporting this community of scholars – the Ravenna Digital Humanities workshop and the consultation with the laboratory STIH "Sens, Texte, Informatique, Histoire” from the University of Sorbonne. Finally, the actual implementation of the Semantic Media Wiki solution for the Haskala research group is presented. Application of knowledge management tools by scholars: 14 scholars have been directly involved in the pilot knowledge management experiment. They are: Prof. Shmuel Feiner, Prof. Zohar Shavit, Prof. Christoph Schulte, Dr Chagit Cohen, Dr Natalie Goldberg, Dr William Hiscott, Dr Tal Kogman, PD Dr Stefan Litt, Prof. Rebecca Voss; Prof. Christian Wiese; Prof. Prof. Michael Brocke, Giuseppe Veltri ; Prof. Michael Miller, Duisburg, Dr Rachel Heuberger. There are several other research teams dealing with the Haskala that are potential users of the database, for example Haskala.net group in the University of Potsdam http://www.haskala.net/mitarbeiter.html and many other historians of the Jewish Enlightenment period. Developing the use of the digitised content by scholars and professionals Five Digital Humanities workshops including hands-on sessions were held in collaboration with WP4 and project partners in London (2), Ravenna and Jerusalem. The total number of scholars exceeded 200.

Deviation from work plan & remedial action

None.

Work Package 3 – Digitisation, metadata entry, API and web

Work package Description

| Work package number : | 3 | Start date: | 4 | End date: | 24 |
| --- | --- | --- | --- | --- | --- |
| Work package title: | Digitisation, metadata entry, API and web |

Objectives for the period

WP3 objectives were to put in place the technical tools required for JUDAICA tasks and provide support for Partners and Associated Partners. It included support for: (1) The digitisation process and issues concerning hardware, software, file formats, design and presentation, storage (2) Content enrichment facilities through an metadata entry system (3) Advanced web management facilities based open source CMS and associated DBMS supporting mash-up from the EUROPEANA open API (4) Semantic interoperability including the representation of controlled vocabularies in RDF/SKOS (5) Selection, installation and support for the use of an open source knowledge management package.

Description of work carried out and achievements

This WP is coordinated by partner AIU. Website Facilities for management of the public Web site of the project were established. Due to the preferences of the Webmaster and other practical considerations it is presently managed using the DreamWeaver package instead of an open source CMS initially foreseen. The back office is maintained using the Moodle open source package. Support to partners concerning the digitisation process. WP3 assembled relevant documentation that provides tutorials and step-by-step support to the partners in planning and implementing the full cycle of the digitisation process. References to such documents were included in the presentation of Jean-Claude Kuperminc (AIU) at the second plenary meeting that took place in London on May 10-11. The British Library, one of Judaica Europeana partners, presented the work it is leading in developing Decision Support Tools in the framework of the IMPACT project. This work is described in the deliverable D3.1 that was delivered by WP3 on time. Metadata ingestion facilities. The active involvement of MiBAC led to close cooperation with the ATHENA project. This enabled WP3 to set metadata ingestion facilities for each of the project partners at the experimental server; a task coordinated by David Klein from the AIU. Mapping metadata and training for the partners. During this period WP3 has collected from the partners XML samples of their metadata. It has carried detailed mapping exercises in which the partners were instructed in the use of the Athena metadata ingestion tool using a hands-on approach. Metadata ingestion facilities. WP3 had to deal with the challenges posed by the wide diversity of institutions (libraries, archives and museums) from which metadata needs to be uploaded to Europeana. This variety is reflected in the structural characteristics of the metadata they provide. The following deliverables were provided by this WP:ators. D3.1 Report on the digitisation of the resources provided by partners (1st version) D3.2 Report on the metadata entry systems of the partners and the procedures for adapting Judaica metadata to Europeana requirements D3.3 Report on the Judaica web facilities and mash-up development based on Europeana APIThis deliverable reports on the progress in regard to API and Mashup. Opportunities to deploy the Europeana API and Widget were sought as soon as they became available. The Europeana widget and geo-location API were installed on Judaica Europeana website using the map search mashup developed in the first Europeana hackaton.. The D3.3 Report on the Judaica web facilities and mash-up developments based on the Europeana API was prepared and delivered on time. D3.4 JUDAICA controlled vocabularies expressed in RDF/SKThis implementation deliverable complements the information presented in the deliverable D2.5 Semantic Interoperability Report with representation of selected controlled vocabularies in RDF/SKOS. That deliverable describes extensively the background concerning applications of RDF/SKOS. It included detailed description of the vocabularies and includes in its final section the description of an experiment applying the SKOSified vocabularies of the Israel Museum Jerusalem for its integration in the semantic interoperability facilities of Europeana. D3.4 document describes several tools that may support the SKOSification of the vocabularies of interests and their maintenance. It also details the considerations in choosing vocabularies for SKOSification: both their potential impact in enhancing access to Jewish cultural heritage content and pragmatic considerations. D3.5 Report on the selection, installation and operation of the knowledge management for collaborative scholarship/curatorship This is an implementation deliverable that complements the information presented in the D2.7 Report on the deployment of a knowledge management system with a pilot focus group. The rationale on which this deliverable is based is presented in that document. Two alternative technical solutions that were considered are presented and the solution that was implemented, the Semantic Media Wiki, is detailed. D3.6 Report on the digitisation of the resources provided by partners (Final version) This deliverable describes how WP3 assembled a list of guidelines and other resources that served the partners in digitising their assets. The inclusion of the National Technical University of Athens (NTUA) as a partner enabled the development of a workflow that successfully implemented the ingestion process. This metadata ingestion service and the expertise of AIU staff enabled the mapping, ingestion and uploading of the metadata to the Europeana ingestion team via OAI-PMH. The Frankfurt University Library, which supplied more than half of the digitized images (1.860.028), carried out the mapping and ingestion of the library content directly into Europeana. Thus, by dividing the task, an effective metadata ingestion process could be established, acting as an important support for the partners, both in discussing problems and experiences and sharing solutions (see section 3.2 under Achievements of the Project).

Deviation from work plan & remedial action

None

Work Package 4 - Awareness and Dissemination

Work package Description

| Work package number : | 4 | Start date: | 0 | End date: | 24 |
| --- | --- | --- | --- | --- | --- |
| Work package title: | Awareness and Dissemination |

Objectives for the period

To raise awareness of the project and promote its results. To promote the JUDAICA Europeana content to the different constituencies across Europe and motivate scholars, teachers and students, cultural heritage professionals to turn to JUDAICA as their primary resource. To promote the JUDAICA system and EUROPEANA to a wider group of public and private content owners and to secure the support of Associate Partners that will contribute additional resources/assets to the project. To ensure synergy between the JUDAICA dissemination and EUROPEANA

Description of work carried out and achievements

WP4 is coordinated by the European Association for Jewish Culture (EAJC) The following 10 deliverables were delivered by WP4 during the project: D4.1 Project Public website D4.2 Multimedia project presentation D4.3 Dissemination Plan D4.4 First Newsletter: D4.5 Project brochure and the 1st of the Workshops to be held at a major conference D4.6 Second Newsletter D4.7 Third Newsletter D4.8 The 2nd of the Workshops to be held at a major conference. D4.9 Final Exploitation Plan D4.10 Multimedia project presentation (results) Public website for the project An attractive website for the project was developed and continues to be updated. It has served as the main platform for the dissemination activities of Judaica Europeana (newsletters, ppt presentations, events). In addition, it provides pages of digital and virtual exhibition resources, news feeds. Other features include a search Europeana collections widget and geo-location API, an automated subscription to the newsletter and the embedding of Bookmark and Share services inc. Email, Facebook, Twitter and some 340 others. Europeana conference videos, a music clip and short features and links to partners virtual exhibitions enhance the home page. The site is available at http//:www.judaica-europeana.eu A screen capture of the home page follows: Judaica Europeana visitor statistics overview (see Annex 2: Googleanalytics reports) Year Visits Hits or unique page views Unique visitors 2010 Project website 12,410 24,986 8,636 2011 Project website 17,611 35,795 12,219 Judaica virtual exhibitions hosted on Europeana June-Oct 2011 From Dada to Surrealism Yiddish Theatre in London 6,231 3,445 46,981 27,466 5,189 3,045 TOTAL 39,697 135,228 29,089 The total number of visits 39,697 and unique page views 135,228 shown above exceed the targets set for the project, which were defined as 1,000 hits per month on average from Month 6 i.e. over a period of 18 months =18,000. In addition, the partner UBFFM (Frankfurt University Library) reports for its Judaica collection the following massive statistics: Visitors statistics from Frankfurt University Library, Judaica Collection Jan 2011 Feb 2011 Mar 2011 Apr 2011 May 2011 Jun 2011 Jul 2011 Aug 2011 Sep 2011 Oct 2011 Nov 2011 Dec 2011 Month Unique visitors Pages Hits Bandwidth Jan 2011 3,148 165,731 357,976 76.28 GB Feb 2011 2,700 239,024 518,488 167.78 GB Mar 2011 4,172 294,170 536,196 103.96 GB Apr 2011 4,180 340,571 557,532 112.34 GB May 2011 4,449 427,600 608,592 136.10 GB Jun 2011 4,119 503,843 660,308 78.79 GB Jul 2011 4,912 570,959 777,810 120.56 GB Aug 2011 4,926 727,122 978,191 174.41 GB Sep 2011 7,604 709,821 987,613 172.89 GB Oct 2011 6,959 707,082 985,428 218.49 GB Nov 2011 7,598 886,356 1,240,161 162.91 GB Dec 2011 8,454 976,611 1,643,952 197.90 GB Total 63,221 6,548,890 9,852,247 1722.41 GB Multimedia project presentation A multimedia powerpoint presentation of the project in progress was published on the public website. It was presented at many meetings and conferences. Different versions of this presentation were prepared, adapted to the needs of the different events at which the project was presented. Dissemination plan The plan outlines dissemination objectives, strategy and identification of target audiences. It includes an overview of dissemination tools and of target institutions and populations, and the alignment of those tools with the target audiences. It presents a list of activities planned by the project partners. The ways of evaluating progress are outlined.The plan was reviewed at Partners’ meetings. A decision was taken to prioritize outreach to the academic community, heritage institutions and educators who are the primary target users of Judaica content. They are also ‘the multipliers’ who can disseminate Judaica content to other users. Newsletters Three Judaica Europeana newsletters were published on the website. These 5-page richly illustrated publications present objects and stories from the Partners’ collections, feature virtual exhibitions, reports on the growing Judaica network, and on Judaica conferences and events. The newsletters were distributed to the subscription list which is based on requests from visitors to the website and other mailing lists incl. the entire membership of the European Association for Jewish studies. The subscription list includes 600 individuals based at universities, museums, libraries and other education centres.http://www.judaicaeuropeana.eu/Newsletter.html Press releases: a press release was distributed prior to the launch of Judaica Europeana. It was translated by the partners and distributed internationally and locally. Many news news agencies and websites relayed the news which aroused much interest. A Google search for “judaica europeana” produced30,100 results in 0.07 seconds. Subsequetly press releases were issued on the occasion of conferences and other events. News were posted on the international H-Judaic academic listserve and on the European Association for Jewish Studies Bulletins and News flashes. A project brochure (D4.5) was produced for distribution at major conferences. It was translated to Partners’ languages and published on the website. Major workshops at international conferences (D4.5 and D4.8) The Workshops constituted key elements of the dissemination plan and were also an important tool in developing Judaica’ work in digital humanities and knowledge management. a) Judaica Europeana’s Workshop on Digital Humanities on 30 July 2010 in collaboration with Action COST A32, "Open Scholarly Communities on the WEB". The Workshop was heldon the Ravenna University Campus at the 9th Congress of the European Association of Jewish Studies. This is a major 5-day international conference, which takes place every 4 years and attracts scholars from all over Europe, USA and Israel. The Deliverable D4.5 provides detailed report on the objectives, programme, participation and feedback from this important workshop. The presentations were published on the Events page of the Judaica website. b) Judaica Europeana’s Workshop on Digital Humanities and the Study of Jewish History and Culture in Europe was held on 31 October 2011 in collaboration with the British Library, a Judaica project partner. The British Library is renowned for its programme of conferences and workshops which reach out to the academic community and proved to be the best possible partner and venue for this Workshop. The objectives, content, participants and evaluation were presented in the deliverable report D4.8. Workshop presentations were published on the public website. c) Judaica Europeana Workshops at the 2011 Annual Conference of the Association of Jewish Museums Two workshop sessions entitled Judaica Europeana: Digitising Collections, Creating Virtual Exhibitions were held on 21 and 22 November 2011 at the AEJM conference for museum professionals from all over Europe. The objectives, content and evaluation of these sessions are provided in D4.8 deliverable. Presentations were published on the Judaica website. Feedback from Judaica Workshop at AEJM Conference, Nov 2011 D4.9 Final Exploitation Plan This deliverable reports on the plans for the exploitation of the content digitized and uploaded by Judaica Europeana to Europeana. The plans provide for the continuation of Judaica Europeana Consortium through a Memorandum of Understanding between partners and allocation of resources by the leading partners EAJC and UBFFM. Participation in a new project – Digital Manuscripts to Europeana – is an important component of the plan as it will provide the facilities for further growth, enrichment and dissemination of Judaica Europeana content. D4.10 Multimedia Project Presentation (Results) This deliverable presents the Multimedia Powerpoint, which showcases the Judaica Europeana project at its conclusion in December 2011. The presentation was produced with the following WP4 objectives in mind: (1) To raise awareness of the project and promote its results.(2) To promote the Judaica Europeana content to the different constituencies across Europe and motivate scholars, teachers, students, cultural heritage professionals and others to turn to Judaica as their primary resource. The presentation places the Judaica Europeana project within the context of Europeana. It presents the historical background on urban Jewish life in Europe, and highlights the results and the achievements of the project. The highlights of the collections are also presented. The ppt contains over 70 richly illustrated slides. It is published on the website in swf (animated) and pdf formats at http://www.judaicaeuropeana.eu/presentation.html Engaging associated partners WP4 made extensive efforts to involve additional institutions as associated partners. This effort provided substantial results: the Judaica network acquired 19 associate partners: Akadem, Campus numérique juif, Paris * Ben Uri Gallery – The London Jewish Museum of Art Biblioteca Rosenthaliana, University of Amsterdam Library Center for Jewish History, New York Central Zionist Archives, Jerusalem Centre francais des musiques juives, Paris * Columbia University Library Harvard University Library Leopold Zunz Zentrum, Halle-Wittenberg Lorand Library, Augsburg University Jewish Historical Museum, Amsterdam * Jewish Museum Berlin Jewish Museum, Frankfurt/Main Medem Library – Paris Yiddish Centre * Ministerio de Cultura, Madrid National Library of Israel, Jerusalem * Paris Yiddish Center—Medem Library * Sephardi Museum, Toledo * Ministerio de Cultura, Madrid Salomon Ludwig Steinheim Institute, Duisberg Six of the above institutions (marked with an asterisk) were in a position to aggregate their collections with Judaica Europeana. Others have more work to do on digitization and/or transformation of their databases. Three institutions with very large collections (Biblioteca Rosenthaliana, Amsterdam, Center for Jewish History, New York and Harvard University Library) will be ready to ingest their content in early 2012. The following institutions are also interested in joining and may do so in the coming year: Aberdeen University Library Jewish Museum of Belgium, Brussels Jewish Community Library and Archives, Venice London Metropolitan Archive Magnes Collection of Jewish Art and Life, Berkeley Mantua City Archives Oxford Centre for Hebrew and Jewish Studies Library Royal Library of Denmark Conferences, seminars and workshops. An extensive programme of conferences, seminars, workshops as well as presentations at international events was implemented: 100 events and presentations were held in 16 countries and 45 different cities. The highlights included a Judaica session on Jewish urban studies at the 9th Congress of the European Association for Jewish Studies in Ravenna; a Workshop on Digital Humanities at the same Congress; an International Judaica Europeana conference in the conjuction with the EVA-Minerva International Jerusalem Conference on Digitisation of Culture, presentation and workshops at the Annual Conferences of the Association of European Jewish Museums in Rome and in London, presentations at Europeana conferences in Berlin, Edinburgh and Madrid (EuropeanaLocal). An almost full list of events giving further information is included in Annex 3.1 A calendar of events with links to programmes and presentations is available at http://www.judaica-europeana.eu/events.html Dissemination of digitised content in higher education: the following university courses were involved in using Judaica primary sources: UK : Jewish studies at Southampton University and University College London (2) Germany: Frankfurt University – history and Yiddish courses (2) Greece: History and archaeology, University of Athens (2) Italy: History and Jewish studies (Universities of Rome, Naples, Macerata) (3) Hungary: History of architecture, St Stephen’s University; Nationalism studies, Central European University (2) Poland: Jewish studies, University of Wroclaw Israel: History, Tel Aviv University and Bar Ilan University (2) Dissemination of digitised content in schools Judaica partners approached schools and teachers in order to encourage the use of Judaica digital resources in teaching and learning. Lessons and presentations to pupils were delivered in 17 schools including: UK: the Daiglan School, London; the North West London Jewish Day School; Italy: the Renzo Levi School in Rome (3 age groups); Hungary: Lauder Javne School and Móricz Zsigmond secondary school in Budapest; France: AIU school in Paris Greece: Athens College, High School of Aegaleo;Varvakeio High School of Athens; Jewish primary school; Zanneio High School; High School of the British Embassy; 1rst High School of Nikaia; International School of Athens; School of Kostea, Geitona Germany: Lichtigfeld school in Frankfurt, where a special programme was developed in cooperation with the Pedagogical Centre of the Jewish Museum/Fritz Bauer Institute. Partners (Poland, Greece, Germany, France, Italy) made also presentations to teachers conferences and groups of educators. Virtual exhibitions Best practice guidelines on planning, designing and marketing of virtual exhibitions were presented and discussed at threeWP4 meetings (May, November 2010, February 2011). Examples of best online exhibitions on Jewish history and culture were collected and published on the Judaica website on the Virtual Exhibitions Resources page. Nine virtual exhibitions were produced by Judaica partners to-date. The exhibitions can be accessed on the Partners’ websites or through the Judaica Home page. A list and descriptions of the exhibitions are presented in this report under Achievements of the Project in section 3.5.2 above. The Googleanalytics statistics for the two exhibitions hosted on Europeana s for the period from June-October 2011, were as follows for the period from June-October 2011: From Dada to Surrealism: 46,981 pageviews, 6,231 visits, 5,189 unique visitors Yiddish Theatre in London: 27,466 pageviews, 3,445 visits, 3,045 unique visitors Crowd-sourced content The Star of David and the Italian Flag (Stella di David e Tricolore) is a successful crowd-sourced, user-generated content initiative developed by MiBAC in the framework of WP4. The Star of David features in effect a series of virtual exhibitions. A more detailed description of this initiative is featured in Annex 3.3 below. http://www.culturaitalia.it/pico/speciali/stella_di_david_e_tricolore/index.html Media coverage of Judaica Europeana Judaica Europeana attracted extensive coverage in the media, partners gave interviews to radio, print and internet media. The internet articles are too numerous to list; a partial listing is presented in Annex 3.2. Many articles were published in scholarly journals. We include here a few examples of the one partner: Rachel Heuberger: Judaica Europeana : Jüdisches Kulturerbe in der virtuellen Welt, (Jewish cultural heritage in the virtual world) in: LBI Information, (Leo Baeck Information) No. 14, 2011, p. 184-191. Interview „Kulturerbe im Netz“, about the exhibition, broadcast on the radio and on the internet-platform of the Radiostation „HR-Online“, November 13th, 2011 Article in the newspaper „Frankfurter Rundschau“ about the exhibition Judaica Europeana vom November 15th, 2011. Article in the University report, „Unireport“, no 6 , December 8th, 2011. Report in„Tribüne. Zeitschrift zum Verständnis des Judentums“ No 50, Issue 200, 2011 Forthcoming Judaica Europeana International (final) Conference 27 February 2012 The one-day programme features presentations by Judaica partners, Europeana staff, scholars, heritage professionals and artists. The conference will be hosted by MiBAC/ICCU at the Central National Library in Rome. http://www.otebac.it/index.php?it/22/archivio-eventi/217/roma-judaica-europeana-international-conference-convegno-internazionale-judaica-europeana

Deviation from work plan & remedial action

None

Work Package 5 - Assessment and Evaluation

| Work package number : | 5 | Start date: | 0 | End date: | 24 |
| --- | --- | --- | --- | --- | --- |
| Work package title: | Assessment and Evaluation |

Objectives for the period

To carry out a comprehensive evaluation showing how the addition of the thematic domain content by JUDAICA leads to an improved practice in the discovery, delivery, integration of cultural heritage resources for European, multilingual, multicultural use by the different target populations: scholars, cultural heritage professionals, education users, cultural tourists and the general public. To carry out in collaboration with other work packages a process-oriented project evaluation and report on the findings.

Description of work carried out and achievements

WP5 is coordinated by Amitie. During the period of this report the following has been accomplished: Identification of success factors Potential target users and their needs were identified and divided into three main categories so as to better focus future surveys. A similar approach was adopted in WP4 to define communication channels and increase effectiveness. Building strong contacts with the main target groups is a good way to gain an insight in the users’ perspectives and to measure usability. Identification of evaluation instruments and planning. An evaluation plan was designed together with a first set of evaluation tools. The plan lays down the methodology and identifies the actors involved in quality monitoring. The areas of activity considered for evaluation cover project management performance, communication/dissemination, sustainability as well as the quality of outcomes. It was presented to the partnership in occasion of the kick-off meeting. Analysis of quantitative and qualitative data. A regular evaluation of the project management has been carried out and the results shared with both the project co-ordinator and the partners. Since the beginning the following meetings have been evaluated: 2nd consortium meeting, hold in Chesham (UK) on the 11th May 2010. 3rd consortium meeting, hold in Ravenna (Italy) on the 27th July 2010. 4th consortium meeting, hold in Jerusalem (Israel) on the 15th November 2010. 5th consortium meeting, hold in Paris (France) on the 7th February 2011 6th consortium meeting, hold in Budapest (Hungary) on the 30th and 31st of May 2011 The second tool for event evaluation have been deployed in several occasions that took place during this period: The Academic Advisory Committee meeting in Ravenna on July 29th 2010 The Digital Humanities Workshop held in Ravenna on July 30th 2010 The International Judaica Europeana conference sessions on November 16th 2010 The information collected in these opportunities provides feedback to the project management and the partners informed the deliverable D5.2 to be issued at the end of the project.

The Commission experts recommended at the mid-term review held in January 2011 that the project should develop a risk management strategy. Subsequently,WP5 developed a risk analysis tool. The tool includes a register of identified risks, their possible impact, their probability, frequency of monitoring, attribution of responsibility among the partners for the monitoring, the appropriate response strategies and action required, and the dates of next review. In order to highlight achievements of the partnership and to gain a more detailed picture on the status of performance, partners engaged in a self-evaluation. For this purpose data was gathered from partners and recorded in a systematic way online via the open source survey software Lime Survey (formerly known as PHP Surveyor). The response was then analysed and the results made available to the project Management Team in an appropriate form. Two reports produced (one for 2010 and one for 2011). A Risk Assessment Process (RAP) was designed, which followed five steps: Step 1 - Identifying risks Step 2 - Evaluating and prioritising risks Step 3 - Recording the findings Step 4 - Deciding on preventive action/mitigation Step 5 - Communicating the findings to the consortium D5.2 Evaluation report measuring the cross-border, multilingual and multicultural use of JUDAICA resources The evaluation report presents the results of a participatory evaluation process. The evaluation was conducted with a particular emphasis on feedback from the users concerning the Judaica digital resources and service. The purpose of the evaluation was to establish how the wide range of digital resources made available by Judaica impacts on the project target audiences and why and how they will use these resources. This outcome-focused evaluation provided an opportunity to voice both criticisms and praise. It was conducted with: internal experts (members of the Academic Advisory Group) who have followed the project throughout its lifespan external stakeholders and potential end users (scholars, researchers, teachers, students). A set of shared questionnaires was developed and used by all project partners sometimes in a slightly customized and/or translated format. This procedure enabled the project to gather valuable information on Judaica target users, their interests, perspective needs and measure their reaction to the outcomes within a shared format. The evaluation was focused on: Quality and consistency of the events presenting Judaica Europeana resources Quality, usefulness, transferability of the digital resources developed by Judaica Europeana Quality and consistency of the virtual exhibitions produced in cooperation with Europeana Multilingual, cross-border use of the digital resources developed by Judaica Europeana based on traffic statistics from Googleanalytics. Evaluation reports have been shared with project partners on the reserved area of the website.

Deviation from work plan & remedial action

None.

# 6.	Deliverables Status

| Deliverable No | Deliverable title | Delivery due date | Actual date of delivery |
| --- | --- | --- | --- |
| D1.1 | Gantt chart of project activities with critical path | M1 | M1 |
| D4.1 | Project public web site | M3 | M3 |
| D4.2 | Multimedia project presentation | M3 | M3 |
| D4.3 | Dissemination plan | M3 | M3 |
| D2.1 | Audit report on JUDAICA content including metadata (1st Version) | M4 | M4 |
| D4.4 | First Newsletter | M6 | M6 |
| D5.1 | Evaluation methodology & targets | M6 | M6 |
| D1.2 | First progress report | M7 | M7 |
| D4.5 | Project brochure and the 1st of the Workshops to be held at a major conference. | M9 | M9 |
| D2.2 | First report of content metadata alignment with Europeana requirements | M12 | M12 |
| D3.1 | Report on the digitisation of the resources provided by partners (1st version) | M12 | M12 |
| D3.2 | Report on the metadata entry systems of the partners and the procedures for adapting Judaica metadata to Europeana requirements | M12 | M12 |
| D4.6 | Second Newsletter | M12 | M12 |
| D1.3 | Second progress report | M13 | M13 |
| D1.4 | Annual Report | M13 | M13 |
| D1.5 | Pre-financing request | M13 | M13 |
| D2.3 | Audit report on Judaica content including metadata (updated and final version) | M18 | M18 |
| D3.3 | Report on the Judaica web facilities and mash-up development based on Europeana API | M18 | M18 |
| D4.7 | Third Newsletter | M18 | M19 |
| D1.6 | Third progress report | M19 | M19 |
| D2.4 | Survey of controlled vocabularies relevant to the thematic domain | M21 | M21 |
| D2.5 | Semantic interoperability report with representation of selected controlled vocabularies in RDF/SKOS | M21 | M21 |
| D2.6 | Second report on content metadata alignment with EUROPEANA requirements | M21 | M21 |
| D3.4 | JUDAICA controlled vocabularies expressed in RDF/SKOS | M21 | M21 |
| D2.7 | Report on the deployment of the knowledge management system with a pilot focus group | M24 | M24 |
| D3.5 | Report on the selection, installation and operation of the knowledge management for collaborative scholarship/curatorship | M24 | M24 |
| D3.6 | Report on the digitisation of the resources provided by partners (final version) | M24 | M24 |
| D4.8 | The 2nd of the Workshops to be held at a major conference. | M24 | M24 |
| D4.9 | Final Exploitation Plan | M24 | M24 |
| D4.10 | Multimedia Project Presentation (results) | M24 | M24 |
| D5.2 | Evaluation report measuring the cross-border, multilingual and multicultural use of JUDAICA resources | M24 | M24 |
| D1.7 | Fourth Progress Report | M25 | M25 |
| D1.8 | Final Project Report | M25 | M25 |
| D1.9 | Final Financial Statement | M25 | M25 |

The Final Financial Statement will be presented following the Final Conference on 27 February 2012.

# 7.	Conclusions

Judaica Europeana succeeded in fulfilling the project objectives. The partners completed the digitisation of their resources, the preparation of the metadata, the mapping and ingestion process for uploading to Europeana. The targets for the quantity of contents to be uploaded to European have been exceeded with metadata records pointing in total to 3.7 million pages/objects provided to Europeana.

The project had to overcome the challenges posed by the diversity of partners from different institutional areas and domains such as libraries, archives and museums. This diversity has demanded that the ingestion of metadata to Europeana be adapted to the constraints of the different metadata systems held by the partners. Managing the mapping process has required a number of solutions to be developed and more extensive efforts than originally expected. The ingestion solutions developed by Judaica Europeana provide valuable guidelines for other content providers to Europeana.

The project followed closely Europeana’s development of its new data model. Judaica carried out pioneering work in surveying controlled vocabularies for Jewish content in cooperation with other leading heritage institutions. Judaica Europeana has secured a controlled vocabulary relevant to the thematic domain from the Israel Museum of Israel and carried out the implementation deliverable. A pilot knowledge management project was developed involving a scholarly database on the Jewish Enlightenment (Haskala) and the application of the semantic media wiki.

A large number of successful high-profile dissemination activities have been carried out: workshops, participation in conferences, other events, newsletter dissemination and virtual exhibitions.

The project created an extensive network of heritage institutions with Jewish content. It provided a unique opportunity for the partners to access wider European networks, build strong relations with external stake holders and reached out to new audiences. The partners’ institutions and staff benefitted greatly from the project: developing new skills and expertise, acquiring digital collections and modernizing their systems.

The project developed an Exploitation Plan and secured the commitment of leading partners, which will ensure the sustainability and continuation of Judaica Europeana.

The deliverables were completed and delivered on time.

# Annex 1:	List of Academic Advisory Group Members

Chair: 	Professor Antony Polonsky

Near Eastern and Judaic Studies, Brandeis University, Cambridge, Mass.

Professor Michael Brenner

Jewish Studies and Culture, University of Munich

Professor Nicholas de Lange

Hebrew and Jewish Studies, University of Cambridge

Dr Anna Foa

Department of History, La Sapienza University, Rome

Professor Gershon Hundert

Jewish Studies, Mc Gill University, Montreal

Editor of The YIVO Encyclopaedia Jews in Eastern Europe

Dr François Guesnet

Department of Hebrew and Jewish Studies, University College London

Professor Rudolf Klein

Architectural historian, Saint Stephen’s University, Budapest

Dr Gadi Luzatto Voghera

Department of Historical Studies, Università Ca' Foscari di Venezia and Centre for Italian and European Studies, Boston University Padova Program;  Director,  Jewish Library and Archives in Venice

Professor Michael L Miller

History Department, Central European University, Budapest

Dr Laura Mincer

Rabbinical College, Rome

Judith Olszowy-Schlanger

Historical and Philological Sciences, École Pratique des Hautes Études, Sorbonne

Simon Tanner

Director, Centre for Computing in the Humanities, Kings College London

Professor Giuseppe Veltri

Jewish Studies, Martin Luther University of Halle-Wittenberg

Professor Marcin Wodzinski

Centre for the Culture and Languages of the Jews, University of Wroclaw

Dr Gerben Zaagsma

Yiddish studies and Yiddish resources on the web, University College London

# Annex 2:	Visitors’ statistics through Googleanalytics

Google Analytics Data for the Web site from February 1st, 2010 to December 31st, 2011

1.	Data for the whole period

2.	Data for each semester

# Annex 3:	Highlights of Dissemination and Awareness Activities

## Annex 3.1	Conferences, workshops and other events

| Date | City, country | Title/subject | Organizing institutions/ project partner | Number of participants | Programme/ presentations on project website |
| --- | --- | --- | --- | --- | --- |
| 2010 |  |  |  |  |  |
| 2 February | Clermont-Ferrand, France | L’Alliance Israélite Universelle, de 1860 à nos jours | L’Alliance Israélite Universelle (AIU) | 45 |  |
| 3 February | Frankfurt, Germany | Judaica Europeana, Jewish Studies, Frankfurt University | JE-UBFFM | 15 |  |
| 2 March | Heidelberg, Germany | Judaica Europeana, Hochschule für Jüdische Studien (University for Jewish Studies) | JE-UBFFM | 18 |  |
| 15 March | Berlin, Germany | Digital Access to Jewish Heritage Collections: Judaica Europeana and MICHAEL Portals seminar | JE with the Institut für Museumsforschung / Institute for Museum Research in Berlin | 30 | Lena Stanley-Clamp: Judaica Europeana digital access to Jewish collections; Rachel Heuberger: Digital access to Jewish collections in Germany; Stefan Rohde-Enslin: Publicizing digital collections in the MICHAEL multilingual portal; Frank von Hagel: Publicizing Jewish content collections |
| 21-24 April | Florence, Italy | Judaica Europeana: Semantic Web tools for expressing the contribution of Jews to European Cities in the European Digital Library – Europeana – Dov Winer; EVA 2010 Florence – Electronic Imaging in the Arts Conference | EVA |  | Pdf, Presentation |
| 28 April | Jerusalem, Israel | Keynote address: Judaica Europeana, Conference of the Israel Association of Judaica Librarians | National Library of Israel | 48 | Presentation |
| 3-5 May | Tel Aviv, Israel | Keynote Address: 'The European Digital Library, Europeana, and Judaica Europeana' – Dov Winer, INFO 2010, the 25th Annual Conference & Exhibition | INFO 2010 | 150 | Presentation |
| 25-27 May | Amsterdam, Netherlands | Keynote Address: Judaica Europeana - content, semantics and meaning for the creative industries' – Dov Winer, WCIT 2010, Creative Industries Track | WCIT 2010, World Congress of Information Technologies |  | Presentation |
| 28-30 May | Bergen, Norway | 'Contents from Europeana and Judaica Europeana for scholarship research and e-learning– Dov Winer, COST A32 Open Scholarly Communities on the Web eLearning Seminar | EAJC and MAKASH | 27 | Presentation |
| 15-16 June | Brussels, Belgium | Judaica Europeana presentation at the: LRE (Learning Resources eXchange) Technical & Semantic Interoperability Workshop | European Schoolnet Learning Resource Exchange (LRE) and the ASPECT Best Practice Network |  |  |
| 28 June | London, UK | Judaica Europeana presentation, Europeana UK Conference | Europeana, Collections Trust, London | 80 |  |
| 4-9 July | Toulouse, France | Colloque international Emmanuel Levinas « Lectures de Difficile Liberté » | AIU | 250 |  |
| 25-29 July | Ravenna, Italy | Judaica Partners presentations on urban Jewish studies and Judaica collections, IX Congress of EAJS | European Association for Jewish Studies | 25 |  |
| 30 July | Bologna, Italy | The Judaica Europeana Digital Humanities Workshop | COST Action 32 Open Scholarly Communities on the Web | 30 | Programme, Presentation Linked Open Data in Digital Humanities – Christian Morbidoni and Michele Barbera (pdf) Everyday Digital Scholarship: using web-based tools for research – Francesca di Donato (pdf) Open Scholarly Communities on the Web: quick start guide Presentation – Matteo d’Alfonso (ppt) Useful examples (ppy) |
| 29 August | Frankfurt am Main, Germany | Judaica Europeana presentation, Limmud Conference | JE-UBFFM | 35 |  |
| 8 September | Paris, France | Exposition « l’Alliance israélite universelle, 150 ans de combat pour l’éducation », Hôtel de Ville | AIU | 6,000 |  |
| 14 September | Heidelberg, Germany | Judaica Europeana presentation, Annual Conference of the Union of Jewish collections in German speaking countries (Arbeitsgemeinschaft Juedischer Sammlungen) | JE-UBFFM | 60 |  |
| 4-5 October | Berlin, Germany | German cultural heritage on its way into Europeana presentation – Dr Rachel Heuberger, National German Europeana Conference | Europeana, JE-UBFFM | 100 |  |
| 7 October | Jerusalem, Israel | Tools and methodology of digital scholarly edition and research, Workshop on Interedition | Judaica Europeana / National Library of Israel | 30 | Pdf |
| 7 October | Frankfurt, Germany | Judaica Europeana presentation – Maike Strobel, Frankfurt International Bookfair | JE-UBFFM | 30 |  |
| 14-15 October | Amsterdam, Netherlands | Europeana Open Culture Conference | Europeana |  |  |
| 19 October | Poznań, Poland | Judaica Europeana presentation – Edyta Kurek, Polish Digital Libraries Conference 2010: Europeana Day | Poznań Supercomputing and Networking Center, Poznań Foundation of Scientific Libraries, The Kórnik Library of the Polish Academy of Sciences, JHI Warsaw | 80 |  |
| 19 October | Nancy, France | L’Alliance Israélite Universelle, de 1860 à nos jours | AIU | 120 |  |
| 21 October | London, UK | Judaica Europeana presentation – Lena Stanley-Clamp, Conference of European Association of Jewish Community Centres, London | European Association of Jewish Community Centres, London | 40 |  |
| 26-27 October | Jerusalem, Israel | Colloque international sur l’histoire de l’AIU, Ben Zvi Institute | AIU | 200 |  |
| 1-2 November | Budapest, Hungary | Judaica Europeana presentations – Jean-Claude Kuperminc and Zsuzsana Toronyi, Limmud Conference | Limmud, AIU | 300 |  |
| 15-16 November | Jerusalem, Israel | Judaica Europeana conference, EVA-Minerva International Conference on the Digitization of Cultural Heritage | EVA-Minerva | 100 | Programme |
| 17 November | Madrid,Spain | Judaica Europeana presentation – Carole Haskel, Europeana Local National Conference | Europeana | 200 |  |
| 17 November | Paris, France | Les Juifs du Maghreb, de l’Exil à l’exode, Alliance israélite universelle | AIU | 230 |  |
| 20-23 November | Rome, Italy | Judaica Europeana and digitization of Jewish collections – Lena Stanley-Clamp, Annual Conference of the Association of European Jewish Museums | Association of European Jewish Museums | 90 |  |
| 2-3 December | Athens, Greece | Teaching about the Holocaust in Greece: 'Judaica Europeana: a digital education tool' – Anastasia Loudarou, Judaica Europeana Seminar | Jewish Museum of Greece | 50 | Presentation |
| 14 December | Edinburgh, UK | Judaica Europeana – Elizabeth Selby, Europeana Scottish Conference | Collections Trust | 60 | Presentation |
| 2011 |  |  |  |  |  |
| 6-30 January | Istanbul, Turkey | Exposition « l’Alliance israélite universelle, 150 ans de combat pour l’éducation » | AIU | 500 |  |
| 14 January | Athens, Greece | Judaica Europeana presentation – Mrs. Zanet Battinou (Director), Official visit and guided tour of JMG by the Israeli Minister for Foreign Affairs, Mr. A. Lieberman. | JMG |  |  |
| 25 January | Athens, Greece | Judaica Europeana and JMG museum presentations for students at 3rd High School of Aegaleo – Mr. Orietta Treveza Soussi, JMG education officer | JMG | 20 |  |
| 27 January | Rome, Italy | Stella di David e Tricolore, Giorno della Memoria 2011, workshop, Biblioteca di Storia moderna e contemporanea | Biblioteca di Storia moderna e contemporanea with Istituto centrale per i beni audiovisivi e sonori, ICCU delle biblioteche italiane | 50 |  |
| 27-28 January | Pisa, Italy | Judaica Europeana presentation, Pisa University Library | JE-ICCU | 40 |  |
| 1 February | Athens, Greece | Judaica Europeana and JMG museum presentations for students at Varvakeio High School of Athens – Mr. Orietta Treveza Soussi, JMG education officer |  | 30 |  |
| 6-7 February | Paris, France | Judaica Europeana Partners’ Meeting | JE |  |  |
| 12 February | Athens, Greece | Judaica Europeana presentation – Mrs. Zanet Battinou (Director), Official visit and guided tour of JMG by Presidents and Directors of European and American Jewish Organizations | JMG | 30 |  |
| 14 February | Athens, Greece | Judaica Europeana presentation – Mrs. Zanet Battinou (Director), Official visit and guided tour of JMG by the President of the US Commission for the Preservation of America’s Heritage Abroad, Mr. Warren Miller and guests | JMG | 5 |  |
| 14-15 February | Milan, Italy | Judaica Europeana presentation, Mediateca Santa Teresa/Braidense Library | JE-ICCU | 100 |  |
| 21 February | Rome, Italy | Judaica Europeana: the Jewish contribution to European culture online – Marzia Piccininno, ICCU delle biblioteche italiane, ATHENA-EuropeanaLocal Workshop European Contribution to online digital cultural heritage | Athena, Europeana | 180 | Presentation |
| 28 February | Athens, Greece | Judaica Europeana and JMG museum presentations for students at Jewish primary school (5th grade) – Mr. Orietta Treveza Soussi, JMG education officer | JMG | 11 |  |
| 1-3 March | Athens, Greece | Judaica Europeana and JMG museum presentations for students at Zanneio High School, High School of the British Embassy and 1st High School of Nikaia – Mr. Orietta Treveza Soussi, JMG education officer |  | 60 |  |
| 14-16 March | Halle/Saale, Germany | The work and impact of Leopold Zunz, the Father of Jewish Studies – Rachel Heuberger, Frankfurt University Library, International Experts Conference | JE-UBFFM | 60 | Programme |
| 22 March | Paris, France | Judaica Europeana presentation –Edyta Kurek, Mémorial de la Shoah | JHI Warsaw | 25 |  |
| 30 March | Warsaw, Poland | Digitization of the Jewish Historical Institute archival collections presented – Agnieszka Reszka, ‘The Legacy of War’ Conference | Department of Victims and Memory, Dutch Ministry of Health, Social Welfare and Sport, Netherlands, Institute of National Remembrance and Jewish Historical Institute, Warsaw | 120 |  |
| 7 April |  | Judaica Europeana and JMG museum presentations for students at International School of Athens (5th grade) – Mr. Orietta Treveza Soussi, JMG education officer | JMG | 13 |  |
| 7-8 April | Genoa, Italy | Judaica Europeana presentation, Library of Regione Liguria | JE-ICCU | 70 |  |
| 11 April | Athens, Greece | Judaica Europeana and JMG museum presentations for students at Department of History and Archaeology, University of Athens – Mr. Orietta Treveza Soussi, JMG education officer | JMG | 40 |  |
| 11 April | Rome, Italy | Online: Europeana e Judaica Europeana Le Città, la Cultura e il Contributo Ebraico all’Europe, Judaica Europeana Conference | JE, Università La Sapienza, Rome | 40 | Programme and presentations |
| 11-13 April | London, UK | Jewish Identities in Contemporary Europe International Conference at the Institute of Germanic and Romance Studies | University of London in association with Judaica Europeana | 50 | Conference abstracts |
| 13-14 April | Southampton, UK | Judaica Europeana – Lena Stanley-Clamp, Toward a Pan-European Survey of Archives with Jewish collections, International workshop | University of Southampton | 40 |  |
| 5 May | Florence, Italy | Judaica Europeana presentation – Marzia Piccininno, Ten years of networking for digital cultural heritage, EVA 2011 Workshop | EVA, JE-ICCU | 20 |  |
| 9-11 May | Paris, France | Colloque international Emmanuel Levinas “Totalité et infini”, Alliance israélite universelle | AIU | 120 |  |
| 16-18 May | Tel Aviv, Israel | Judaica Europeana presentation – Dov Winer, INFO 2011 Conference | INFO 2011 |  |  |
| 16-19 May | Buenos Aires, Argentina | Judaica Europeana presentation – Edyta Kurek, at: Philosophy Faculty, Buenos Aires University Sherit Hapleita, Generaciones de la Shoá, Anne Frank Center, IWO, AMIA (Argentinian Jewish Community) and Holocaust Museum (Museo del Holocausto) | JHI Warsaw | 170 | 16-19 May |
| 18 May | Athens, Greece | Judaica Europeana and JMG museum presentations for students at School of Kostea- Geitona – Mr. Orietta Treveza Soussi, JMG education officer | JMG | 50 |  |
| 24-28 June | Warsaw, Poland | Judaica Europeana presentation – Edyta Kurek, Summer Academy for Polish Teachers | JHI Warsaw | 50 |  |
| 30 June | Krakow, Poland | Five (P)Arts Inspired by the text of five Megilloth, a modern interpretation of the Song of Songs performed in five different art idioms. A Midrash Theatre production directed by Tanya Segal, Jewish Museum Galicia, Jewish Culture Festival, Krakow | JE co-sponsor | 50 |  |
| 7 July | Paris, France | Journées européennes de la culture juive, présentation, Médiathèque Alliance Baron Edmond de Rothschild | AIU | 200 |  |
| 8 July | Oświęcim, Warsaw | Judaica Europeana project presentation – Edyta Kurek, for American students, Auschwitz Jewish Center | JHI Warsaw | 25 |  |
| 6-10 August | Frankfurt/Main, Germany | Judaica Europeana Workshop on digitized primary resources for Jewish studies – Rachel Heuberger, Summer School for PhD Students in Modern European Jewish History and German Jewish Studies, Goethe University Frankfurt/Main | JE_UBFFM in co-operation with Prof. Christian Wiese, Martin-Buber-Professor for Jewish religious philosophy at the Frankfurt University | 45 |  |
| 7 August | Lublin, Warsaw | Judaica Europeana presentation – Edyta Kurek, for Polish-German-Ukrainian participants of the educational project by “Studnia Pamięci” Association | JHI Warsaw | 15 |  |
| 11 August | Jerusalem, Israel | Semantic MediaWiki and the Haskala Project: Building a modern Jewish Republic of Letters in the 18th and 19th Century using the Semantic Web workshop | The National Library of Israel and Judaica Europeana |  | Yaron Koren, Introduction to the Semantic Web (Pdf) Yaron Koren, The "Semantic Bundle" (Pdf) |
| 20 August | Warsaw, Poland | Judaica Europeana presentation – Edyta Kurek, International Children of the Holocaust Conference | JHI Warsaw | 120 |  |
| 31 August | Frankfurt, Germany | Judaica Europeana lecture – The Frankfurt digital library of Jewish cultural heritage in the framework of the culture program of the Radiostation HR2 | JE-UBFFM | 40 |  |
| 4 September | Siena-Modena, Italy | Judaica Europeana presentation, Europeana and Stella di Davide, Jewish Culture Day | JE-ICCU | 200 |  |
| 13-14 September | Nowy Sącz, Poland | Judaica Europeana presentation – Edyta Kurek, educational conference | Regional Museum of Nowy Sącz and the Main Pedagogical Library in Nowy Sącz, JHI Warsaw | 200 |  |
| 15 September | Hamburg, Germany | Judaica Europeana and digital resources of European Jewry presentation – Maike Strobel, Annual conference of the Union of Jewish collections in German speaking countries (Arbeitsgemeinschaft Juedischer Sammlungen) | JE-UBFFM | 65 |  |
| 21 September | Paris, France | Visite de l’Association des bibliothécaires catholiques français, Alliance israélite universelle | AIU | 25 |  |
| 21 September | Trier, Germany | Judaica Europeana: rare sources of the Yiddish Theatre on its way to become an online resource presentation – Ute Müller | JE-UBFFM | 75 |  |
| 26 September | London, UK | Semantic MediaWiki: a tool for collaborative databases workshop; Judaica Europeana Haskala Database and Semantic MediaWiki lecture – Yaron Koren, semantic MediaWiki developers, New York | Centre for e-Research, King’s College London | 40 |  |
| 6-7 October | Fermo, Italy | Jewish presence and heritage: research and enhancement. The Judaica Europeana project | JE-ICCU, Department of Cultural Heritage, University of Macerata |  |  |
| 12 October | Athens, Greece | Lighting devices in Byzantium international conference – Mrs. Anastasia Loudarou, JMG | JMG | 40 |  |
| 13-15 October | Frankfurt, Germany | Judaica Europeana presentations – Maike Strobel, Frankfurt Bookfair | JE-UBFFM | 55 |  |
| 20 October | Warsaw. Poland | Judaica Europeana presentation – Edyta Kurek, Agnieszka Reszka, for Austrian Deputy Minister of Foreign Affairs | JHI Warsaw | 4 |  |
| 28 October | Rome, Italy | Judaica and Stella di Davide, How Judaica materials in Europeana can be used in a lesson (using postcards in Hungarian collections), | ICCU and School "Renzo Levi" in Rome Ghetto | 50 |  |
| 31 October | London, UK | Judaica Europeana and Digital Humanities Workshop | Judaica Europeana and the British Library |  | Programme and presentations: 1. Digital innovation and access to Europe's heritage online: the strategy of Europeana.eu (Ppt) J Purday, Europeana 2. Judaica Europeana: library, archive and museum collections online from Europe and beyond (Pptx) L Stanley-Clamp, Judaica Europeana project manager 3. Integrating user environments and data liquidity to improve the research experience (Ppt) Chris Clark, British Library 4. Collaborative research online: the knowledge management pilot project on Haskala, the Jewish enlightenment database (Ppt) Rachel Heuberger, Frankfurt University Library 5. Scholarship, tools, research practices (Pptx) Sheila Anderson, Centre for e-research, King's College London 6. Facilitating data mining: Tagging the digitized Montefiore Testimonials (Ppt) Francois Guesnet, University College, London 7. Internet resources for historical research: Jewish content in a broader context (Pdf) Gerben Zaagsma, Huygens Institute for Dutch History, The Hague 8. A Judaica Europeana virtual exhibition: Yiddish Theatre in London (Ppt) Elizabeth Selby, Jewish Museum London 9. Future Perspectives (Pptx) Simon Tanner, King's College London |
| 1 November | Athens, Greece | Judaica Europeana and JMG museum presentations for students at Athens College – Mr. Orietta Treveza Soussi, JMG education officer | JMG | 100 |  |
| 9-10 November | New York, USA | From Access to Integration: Digital Technologies and the Study of Jewish History, international conference at Center for Jewish History | Center for Jewish History, JE-UBFFM, AIU | 130+500 |  |
| 13 November | London, UK | Stranger at the Table, a staged reading of the new historical play by Julia Pascal | Jewish Museum London |  |  |
| 14 November | Warsaw, Poland | Judaica Europeana presentation – Edyta Kurek, for students of the Holocaust Faculty at European Institute, Jagiellonian University | JHI Warsaw | 20 |  |
| 14-30 November | Montréal, Canada | Exposition « l’Alliance israélite universelle, 150 ans de combat pour l’éducation » | AIU | 1500 |  |
| 15 November | Frankfurt, Germany | Judaica Europeana lecture, opening of the exhibition on Judaica Europeana, Kunstbibliothek – Städelbibliothek | JE_UBFFM in co-operation with the Kunstbibliothek – Städelbibliothek (Art Library) of the Frankfurt University | 60 |  |
| 16 November | Jerusalem, Israel | Judaica Europeana sessions, EVA/Minerva Annual Conference on Digital Heritage, Van Leer Institute | EVA/Minerva, Van Leer Institute |  | The Haskala Republic of Letters Research Project, Dr Stefan Litt, National Library of Israel The Holocaust Theatre Collection Online, M. Ejlenberg, All About Jewish Theatre Judaica Europeana 2012-2014, Dov Winer, Judaica Europeana |
| 17 November | Naples, Italy | Sharing, collaboration, knowledge: Jewish culture in the Internet age Interdisciplinary seminar at the Centre for Jewish Studies, University of Naples | In association with MiBAC/ICCU- Judaica Europeana and Jewish Community of Naples | 80 | Presentation |
| 19-22 November | London, UK | Annual Conference of the Association of European Jewish Museums including a workshop on ‘Digitising Collections and Creating Virtual Exhibitions’ | Jewish Museum of London | 100 / 40 | Introduction to digitisation of collections (Ppt) Introduction to creating virtual exhibitions (Ppt) Liz Selby and Helena Liszka, Jewish Museum London |
| 22 November | Barcelona, Spain | Europeana, agregació de continguts i Linked Data pel patrimoni cultural Workshop Citilab, Cornellà-Barcelona | JE, Europeana |  |  |
| 24 November | Frankfurt, Germany | Judaica Europeana presentation, book launch of the German translation of the Argentine classical work Jewish Gauchos by Alberto Gerchunoff | Argentine General consulate, Frankfurt in co-operation with the Frankfurt University, JE-UBFFM | 50 |  |
| 27 November | Rome, Italy | Dalle rotative all'iPad – tradizione a future nella stampa ebraica | Judaica Europeana in association with ICCU and Unione delle Comunità ebraiche italiane (UCEI) | 50 | Pdf |
| 1 December | Bari, Italy | Judaica Europeana and Stella di David, Conference Il Mezzogiorno, la Puglia, la memoria storica nel processo di Unificazione nazionale | University of Bari, ICCU | 50 |  |
| 3 December | Athens, Greece | “Teaching about the Holocaust in Greece” seminar, virtual exhibition Images of the Greek Jews and Judaica Europeana presentations to Greek educators – Mr. Orietta Treveza Soussi, JMG education officer | JMG | 40 |  |
| 25 December | Israel | Judaica Europeana presentation – Edyta Kurek, Massuah archives, conference for Holocaust educators | JHI Wasaw | 80 |  |
| 2012 |  |  |  |  |  |
| 18 January | Warsaw, Poland | Judaica Europeana presentation – Agnieszka Reszka, project for students of Jewish Studies Faculty at History Department Warsaw University | JHI Warsaw | 30 |  |
| 26 January | Bari, Italy | Memoria storica e web: Judaica Europeana – Marzia Piccinino and Maria Teresa Natale, ICCU, Rome | Soprintendenza Archivistica per la Puglia and MiBAC-ICCU |  | Presentations |
| 27 February | Rome, Italy | Judaica Europeana and the Jewish cultural heritage in Europe, International Conference | JE-ICCU, Central National Library, Rome |  | Programme. Presentations will be published after the conference |

## Annex 3.2 		Judaica Europeana in the media

| Media source & date | Title | URL |
| --- | --- | --- |
| Research Information 14.2.2010 | Europeana adds Jewish culture | http://www.researchinformation.info/news/news_story.php?news_id=575 |
| M & C 12.2.2010 | Jewish literature and artefacts to be available online | http://www.monstersandcritics.com/news/europe/news/article_1533127.php/Jewish-literature-and-artefacts-to-be-available-online |
| 9.2.2010 | EC funds Jewish museums to go digital | http://www.thejc.com/news/world-news/26970/ec-funds-jewish-museums-go-digital |
| 11.2.2010 | Digital Judaica Project To Provide Multilingual Access to Collections | http://ejewishphilanthropy.com/digital-judaica-project-to-provide-multilingual-access/ |
| Jewish Telegraphic Agency 11.2.2010 | Project will provide online Judaica access | JTA- Jewish & Israel News.mht |
| ALGEMENE BRONNEN en INFORMATIE 10.2.2010 | Judaica Europeana will work with European institutions |  |
| Europeana Newsletter January 2010 | New Projects Launched: JUDAICA Europeana and EUscreen |  |
| Idw Informationsdienst Wissenschaft 12.2.2010 | 'Judaica Europeana': Mehrsprachiger Zugriff auf jüdische Kulturgüter im Digitalformat | Goethe University Frankfurt http://idw-online.de/pages/de |
| Resource Shelf 10.2.2010 | Digitisation Project: European Commission Funds Jewish Museums to Go Digital | http://web.resourceshelf.com/go/resourceblog/57467 |
| Genealogien und Familienforschung 12.2.10 | Judaica Europeana: Mehrsprachiger Zugriff... | http://www.rambow.de/ |
| Uninews online 12.2.10 | Judaica Europeana startet mit 1,5 Millionen Euro Fördergeld | http://uninews-online.de/ |
| Nations Presse Info 12.2.10 | La Commission européenne soutient les musées juifs dans leur passage au numérique | http://www.nationspresse.info/ |
| ICA | http://www.icaol.org/canali-tematici/eventi-arte-e-spettacolo/item/88-stella-di-david-e-tricolore-gli-ebrei-e-la-costruzione-dell%E2%80%99italia-unita?tmpl=component&print=1 |
| INFORMAZIONE.TV | http://www.golosariapiazzetta.it/index.php?action=index&p=59&art=30726 |
| CULTURAMARCHE | http://www.cultura.marche.it/CMDirector.aspx?id=10399 |
| LA SAPIENZA | http://www.uniroma1.it/sapienza/archivionotizie/online-europeana-e-judaica-europeana-le-citt%C3%A0-la-cultura-e-il-contributo |
| SASSUOLO 2000 | http://www.sassuolo2000.it/2011/09/01/modena-una-giornata-per-lebraismo-che-guarda-al-futuro/ |
| GAZZETTA DEL MEZZOGIORNO | http://www.lagazzettadelmezzogiorno.it/notizia.php?IDCategoria=2699&IDNotizia=486635 |
| RADIO POPOLARE SALENTO | http://www.radiopopolaresalento.it/2012/01/19/un-mese-di-eventi-in-puglia-per-ricordare-la-shoah/ |
| UNIMC | http://www.unimc.it/conferenze/index.php/judaica/j |
| MOVIMENTI CULTURALI | http://movimenti.ning.com/events/11-aprile-judaica-europeana |
| BOOK NEXT | http://www.biblionext.it/profiles/blogs/judaica-europeana |
| UNIVERSITA' LA SAPIENZA | http://www.dipscr.uniroma1.it/?q=node/902 |
| BIBLIOTECA D'ISRAELE | http://bibliotecadisraele.wordpress.com/2011/10/06/europeana-judaica-convegno-testimonianze-della-cultura-ebraica-ricerca-e-valorizzazione-il-programma/ |
| MOKED | http://moked.it/blog/2011/04/12/qui-roma-limmenso-patrimonio-ebraico-riunito-online/ |
| ICCU | http://www.iccu.sbn.it/opencms/opencms/it/main/attivita/internaz/pagina_380.html |
|  | www.judaica-europeana.eu |
|  | http://www.judaica-europeana.eu/Downloads/ATHENA_21022011_Roma_patrimonioculturale_JUDAICA_Piccininno.pdf |
| INTERNET CULTURALE | http://www.internetculturale.it/opencms/opencms/it/archivionovita/2011/novita_0045.html |
| OPIB | http://www.opib.librari.beniculturali.it/italiano/progetti/JudaicaEuropeana.htm |
| CULTURAITALIA | http://www.culturaitalia.it/pico/speciali/stella_di_david_e_tricolore/index.html |
| moked/מוקד il portale dell'ebraismo italiano | http://www.moked.it/unione_informa/111128/111128.html |
| INDICATE | http://www.indicate-project.eu/index.php?en/22/events-archive/43/roma-il-contributo-europeo-al-patrimonio-culturale-in-digitale-sul-web-the-europe |
| BIBLIOTECHE APERTE | http://www.bibliotecheaperte.it/joomla/index.php?view=details&id=771%3ATestimonianze+della+cultura+ebraica%3A+ricerca+e+valorizzazione.+Il+progetto+Judaica+Europeana&option=com_eventlist&Itemid=18 |
| MEDI@TV GLOBAL COMMUNICATION | http://www.mediatvcom.it/index.php?option=com_content&view=article&id=209:convegno-qtestimonianze-della-cultura-ebraica-ricerca-evalorizzazioneq-il-progetto-judaica-europeana-fermo-6-7-ottobre-2011&catid=3:notizie |
| POLO SBN DI BIBLIOTECHE ECCLESIASTICHE | http://www.polopbe.it/beniculturali/pbe/00024012_Progetto_Europeana_Judaica__incontri_a_Napoli_e_Roma.html |
| NOODLS | http://www.noodls.com/viewNoodl/9620957/universit224-degli-studi-di-roma-la-sapienza/11042011-online-europeana-e-judaica-europeana-le-citt |
| SITO NOACHIDE | http://www.benenoach.info/dblog/articolo.asp?articolo=143 |
| MINERVA | http://www.minervaeurope.org/news/newsita1022.html |
| ISTITUTO POLACCO DI ROMA | http://www.istitutopolacco.it/index.php?mod=2&evLungo=256&c_month=11&c_year=2011 |
| IL VELINO AGV | http://www.ilvelino.it/agv/news/abbonamenti.php |
| IL RESTO DEL CARLINO | http://www.ilrestodelcarlino.it/fermo/cultura/2011/10/06/594820-dove_andiamo_oggi.shtml |
| IL SOLE 24 ORE | http://www.ilsole24ore.com/art/cultura/2011-09-04/ebrismo-nostri-giorni-081611.shtml?uuid=AaCgZP1D |
| STORIA DIGITALE | http://www.storiadigitale.it/blog/stella-di-david-e-tricolore-culturaitalia-un-patrimonio-da-esplorare |
| MARCHEMANIA | http://www.marchemania.it/marche/fermo/convegno-testimonianze-della-cultura-ebraica-ricerca-e-valorizzazione.html |
| IL MASCALZONE | http://www.ilmascalzone.it/2011/10/dallunimc-56/ |
| PAPER BLOG | http://it.paperblog.com/nel-caso-passaste-da-londra-il-31-ottobre-e-comprendeste-l-inglese-613941/ |
| Evangelici d’Italia per Israele | http://www.edipi.net/index.php?option=com_k2&view=item&id=6398:convegno-testimonianze-della-cultura-ebraica-ricerca-e-valorizzazione&lang=en |
| LAPRIMAWEB | http://www.laprimaweb.it/2011/10/05/testimonianze-della-cultura-ebraica-ricerca-e-valorizzazione/ |
| ARCHIVIO CENTRALE DELLO STATO | http://www.acs.beniculturali.it/index.php?it/21/news/29/eva-2011-workshop-ten-years-of-networking-for-digital-cultural-heritage |

## Annex 3.3:		Stella di David e tricolore, a crowd sourcing content initiative

CulturaItalia, The Star of David and the Italian Flag

Many initiatives have been carried on by Italian cultural institutions in the framework of the celebrations for the 150 anniversary of the unification of Italy. In the framework of Judaica Europeana, ICCU contributed with the initiative "Star of David and the Italian flag", a project aimed at promoting Jewish culture in collaboration with CulturaItalia, the portal of Italian culture, managed by the Italian Ministry of Cultural Heritage.

This initiative is targeted to institutions and individuals, who are invited to submit cultural content in digital format documenting th history and traditions of Italian Jewish Communities in the 150 years since the proclamation of Italian Unification for publication  in a dedicated space within the portal of the Italian culture.

Users may submit stories, images, documents, videos, audios, books, journals, articles, etc, aiming at illustrating  customs and traditions that change over time, participation in political life, integration and migration, but also religion, before and after the Concordat, culture, participation in Risorgimento and all what may represent the history of the relationship between Judaism and unification of Italy.

The initiative, started in the first months of 2011 will continue after the end of the project.

To-date many Jewish communities, archives, journals, artists, as well as private citizens have contributed with hundreds of digitised pages, images, MP3, videos and documents.

This initiative represents a valuable resource for all those involved in the project:

- for institutions that  started the work of digitization of their collections

- for the research community and other users

- for teachers to whom if offers ideas and materials for seminars and courses in schools.

http://www.culturaitalia.it/pico/speciali/stella_di_david_e_tricolore/index.html

A snapshot of the varied content provided by this initiative is presented below. Further highlights  are presented in the Judaica Multimedia Presentation (results) on the public website

# Footnotes

OJ L 79, 24.3.2005, p. 1.